## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS | SM/18186 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 61/BD-1/28 | 27/04/2023 | 27/04/2023 | Resource Division | 16.52 | 0 | 0 | 0
2 | MURSHIDABAD | Lalgola | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS | SM/18186 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 304/BD-1/11 | 22/02/2024 | 22/02/2024 | Resource Division | 6.42 | 0 | 0 | 0
3 | MURSHIDABAD | Lalgola | Berhampore Mechanical | NAMOORAHAR AND ADJOINING MOUJAS PWSS | SM/18186 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III under NAMOORAHAR ground water based water supply scheme under Block_ LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000026/2025-2026 | 1159/MEDB | 15/05/2025 | 15/08/2025 | MASSK ENGINEERING WORKS | 10.65 | 0 | 0 | 0
4 | MURSHIDABAD | Lalgola | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS | SM/18186 | New | NAMOORAHAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000080/2023-2024 | 732/BD-I | 16/08/2023 | 14/11/2023 | MASOOM TRADERS | 34.64 | 0 | 0 | 25
5 | MURSHIDABAD | Lalgola | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS | SM/18186 | New | NAMOORAHAR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte | Assistant Engineer,Assistant Engineer-I | JE | ORD/000195/2023-2024 | 746/BD-I | 17/08/2023 | 01/01/2026 | M/S. UNIQUE BUILDERS | 244.5 | 103.36 | 42.27 | 10
6 | MURSHIDABAD | Lalgola | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS | SM/18186 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NAMOORAHAR PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division-I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | Assistant Engineer |  | ORD/000003/2025-2026 | 547/BD-I | 09/04/2025 | 24/04/2025 | BHOWMIK CONSTRUCTION | 8.99 | 0 | 0 | 0
7 | MURSHIDABAD | Lalgola | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS | SM/18186 | New | Bored Cast-in-situ_ M30 _ grade 600 mm dia 22.00 m (shaft Length) R.C.C. pile for Construction of OHR at Head Work site of NAMOORAHAR Ground Piped Water Supply Scheme under Jal ivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000327/2024-2025 | 270/BD-I | 11/02/2025 | 01/07/2025 | M/S. UNIQUE BUILDERS | 19.08 | 0 | 0 | 100
Total | [13 empty] | 340.8 | 103.36 | 30.33