## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Mechanical | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BAYRA ground water based water supply scheme under Block_LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001433/2023-2024 | 4313/MEDB | 29/12/2023 | 29/03/2024 | HARA PROSAD DAS | 33.24 | 0 | 0 | 0
2 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 304/BD-1/6 | 22/02/2024 | 22/02/2024 | Resource Division | 24.04 | 0 | 0 | 0
3 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 201/BD-1/26 | 10/02/2024 | 10/02/2024 | Resource Division | 39.6 | 0 | 0 | 0
4 | MURSHIDABAD | Lalgola | Berhampore Mechanical | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | NEW CONNECTION BAYRA PH-1 |  |  | BILL/01513/2023-2024 | 388/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 6.05 | 0 | 0 | 0
5 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000147/2023-2024 | 634/BD-I | 04/08/2023 | 03/08/2026 | M/S GHOSH AND CO | 383.82 | 0 | 0 | 50
6 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000118/2023-2024 | 512/BD-I | 25/07/2023 | 26/12/2025 | SRIJON ENTERPRISE | 244.14 | 0 | 0 | 30
7 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000137/2023-2024 | 620/BD-I | 03/08/2023 | 01/02/2025 | RAJEN DAS | 55.72 | 0 | 0 | 50
8 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte.. | Assistant Engineer | JE | ORD/000341/2023-2024 | 1255/BD-I | 22/12/2023 | 11/03/2025 | MASOOM TRADERS | 61.36 | 0 | 0 | 30
9 | MURSHIDABAD | Lalgola | Central Drilling | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Continuation for Hiring of Diesel driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000057/2024-2025 | 238/S&WSD | 24/12/2024 | 24/06/2025 | NAGENDRA PATRA | 0.86 | 0 | 0 | 0
10 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAYRA PWSS(TW-I&II) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | Assistant Engineer |  | ORD/000378/2024-2025 | 438/BD-I | 20/03/2025 | 19/04/2025 | HARUN ALL RASHID & BROTHERS | 17.97 | 0 | 0 | 0
Total | [13 empty] | 866.81 | 0 | 0