## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Mechanical | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BAYRA ground water based water supply scheme under Block_LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001433/2023-2024 | 4313/MEDB | 29/12/2023 | 29/03/2024 | HARA PROSAD DAS | 33.24 | 0 | 0 | 0
2 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 304/BD-1/6 | 22/02/2024 | 22/02/2024 | Resource Division | 24.04 | 0 | 0 | 0
3 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 201/BD-1/26 | 10/02/2024 | 10/02/2024 | Resource Division | 39.6 | 0 | 0 | 0
4 | MURSHIDABAD | Lalgola | Berhampore Mechanical | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | NEW CONNECTION BAYRA PH-1 |  |  | BILL/01513/2023-2024 | 388/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 6.05 | 0 | 0 | 0
5 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000147/2023-2024 | 634/BD-I | 04/08/2023 | 03/08/2026 | M/S GHOSH AND CO | 383.82 | 0 | 0 | 50
6 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000118/2023-2024 | 512/BD-I | 25/07/2023 | 26/12/2025 | SRIJON ENTERPRISE | 244.14 | 0 | 0 | 30
7 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000137/2023-2024 | 620/BD-I | 03/08/2023 | 01/02/2025 | RAJEN DAS | 55.72 | 11.76 | 21.11 | 50
8 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte.. | Assistant Engineer | JE | ORD/000341/2023-2024 | 1255/BD-I | 22/12/2023 | 11/03/2025 | MASOOM TRADERS | 61.36 | 4.85 | 7.9 | 30
9 | MURSHIDABAD | Lalgola | Central Drilling | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Continuation for Hiring of Diesel driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000057/2024-2025 | 238/S&WSD | 24/12/2024 | 24/06/2025 | NAGENDRA PATRA | 0.86 | 2.1 | 242.74 | 0
10 | MURSHIDABAD | Lalgola | Central Drilling | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 14.36 | 1.99 | 20
11 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Designing, making and errection of Display Board for Scheme information by using Logo and tag line of Jal Jeevan Mission at different PWSS work sites in the district of Murshidabad under Berhampore Division-I, PHE Dte. (Block :- Raninagar - I, Raninagar - II, Beldanga - I, Beldanga - II, Jalangi & Nowda) | Assistant Engineer-II | Junior Engineer | ORD/000134/2024-2025 | 1532/BD-I | 19/09/2024 | 19/10/2024 | SUMAN ENTERPRISE AND SUMAN AQUA | 18.91 | 10.11 | 53.45 | 54
12 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAYRA PWSS(TW-I&II) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | Assistant Engineer |  | ORD/000378/2024-2025 | 438/BD-I | 20/03/2025 | 19/04/2025 | HARUN ALL RASHID & BROTHERS | 17.97 | 0 | 0 | 0
Total | [13 empty] | 1605.95 | 43.18 | 2.69