## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer-I |  | ORD/000182/2023-2024 | 698/BD-I | 11/08/2023 | 07/02/2024 | JAHANGIR ALAM | 263.59 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 750 cum) under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000202/2023-2024 | 846/BD-I | 05/09/2023 | 11/07/2024 | JAHANGIR ALAM | 466.95 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 201/BD-1/5 | 10/02/2024 | 10/02/2024 | Resource Division | 86.32 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola-II | Berhampore Mechanical | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NEW CONNECTION NASIPUR PH-1 |  |  | BILL/01575/2023-2024 | 410/WBSEDCL-JJM | 06/03/2024 | 06/03/2024 | WBSEDCL | 21.19 | 0 | 0 | 0
5 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000183/2023-2024 | 701/BD-I | 11/08/2023 | 27/01/2026 | RAJ KUMAR MONDAL | 193.43 | 0 | 0 | 5
6 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000340/2023-2024 | 1254/BD-I | 22/12/2023 | 21/03/2024 | MASOOM TRADERS | 56.23 | 3.94 | 7.02 | 25
7 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR and Adjoining Mouzas PWSS (TW- I, II, III & IV Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (04 Nos TW) | Assistant Engineer-I |  | ORD/000062/2025-2026 | 774/BD-I | 22/05/2025 | 06/07/2025 | SARKAR WATER SUPPLY AGENCY | 36.02 | 0 | 0 | 0
8 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | Designing, making and errection of Display Board for Scheme information by using Logo and tag line of Jal Jeevan Mission at different PWSS work sites in the district of Murshidabad under Berhampore Division-I, PHE Dte. (Block :- Lalgola, Bhagwangola - I, Bhagwangola - II, Farakka, Berhampore, Murshidabad-Jiaganj, Nabagram & Hariharpara). | Assistant Engineer-I | Junior Engineer | ORD/000133/2024-2025 | 1531/BD-I | 19/09/2024 | 19/10/2024 | AJOY GHOSH | 21.44 | 21.01 | 97.99 | 70
Total | [13 empty] | 1145.16 | 24.95 | 2.18