## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer-I |  | ORD/000182/2023-2024 | 698/BD-I | 11/08/2023 | 07/02/2024 | JAHANGIR ALAM | 263.59 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 750 cum) under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000202/2023-2024 | 846/BD-I | 05/09/2023 | 11/07/2024 | JAHANGIR ALAM | 466.95 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 201/BD-1/5 | 10/02/2024 | 10/02/2024 | Resource Division | 86.32 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola-II | Berhampore Mechanical | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NEW CONNECTION NASIPUR PH-1 |  |  | BILL/01575/2023-2024 | 410/WBSEDCL-JJM | 06/03/2024 | 06/03/2024 | WBSEDCL | 21.19 | 0 | 0 | 0
5 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000183/2023-2024 | 701/BD-I | 11/08/2023 | 27/01/2026 | RAJ KUMAR MONDAL | 193.43 | 0 | 0 | 5
6 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000340/2023-2024 | 1254/BD-I | 22/12/2023 | 21/03/2024 | MASOOM TRADERS | 56.23 | 0 | 0 | 25
7 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR and Adjoining Mouzas PWSS (TW- I, II, III & IV Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (04 Nos TW) | Assistant Engineer-I |  | ORD/000062/2025-2026 | 774/BD-I | 22/05/2025 | 06/07/2025 | SARKAR WATER SUPPLY AGENCY | 36.02 | 0 | 0 | 0
Total | [13 empty] | 1123.73 | 0 | 0