## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | Augmentation | Repair And Renovation Works Of OHR (350 Cum) of Ground Water Based Supply Scheme for Bishnupur Zone-I of Raninagar-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer | JE | ORD/000250/2023-2024 | 1034/BD-I | 01/11/2023 | 01/12/2023 | ARJU CONSTRUCTION | 8.5 | 6.71 | 78.86 | 100
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 194/BD-I/5 | 09/02/2024 | 09/02/2024 | Resource Division | 56.41 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | Augmentation | NEW CONNECTION AT BISHNUPUR PRATAPUR Z-I PH-I |  |  | BILL/01630/2023-2024 | 468/WBSEDCL-JJM | 19/03/2024 | 19/03/2024 | WBSEDCL | 6.75 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | Augmentation | NEW CONNECTION BISHNUPUR PRATAPUR Z-I PH-II |  |  | BILL/01628/2023-2024 | 467/WBSEDCL-JJM | 19/03/2024 | 19/03/2024 | WBSEDCL | 1.74 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Bishnupur Zone-I ground water supply scheme in Raninagar-I Block Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000006/2025-2026 | 1130/MEDB | 13/05/2025 | 13/08/2025 | SREE RADHA ELECTRICAL | 39.95 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | Augmentation | Augmentation of Bishnupur Zone-I Piped water supply scheme to accommodate construction of OHR, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | JE | ORD/000141/2023-2024 | 627/BD-I | 04/08/2023 | 31/08/2026 | NATIONAL CONSTRUCTION | 452.24 | 347.4 | 76.82 | 25
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | Augmentation | BISHNUPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000085/2024-2025 | 1265/BD-I | 01/08/2024 | 28/05/2025 | SHIBAM ENTERPRISE | 21.91 | 0 | 0 | 80
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of Bishnupur Zone-I PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1304/BD-I | 07/08/2024 | 06/10/2024 | M/S BHAGIRATHI ENTERPRISE | 7.65 | 0 | 0 | 0
9 | MURSHIDABAD |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 14.89 | 2.07 | 20
10 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 80 Cum/hr.) with allied work at Bishnupur Zone-I Water Supply Scheme under Jal Jeevan Mission of Raninagar-I under Berhampore Division-I, PHEengineering Dte. | Assistant Engineer | JE_Pravin Kumar Gupta | ORD/000009/2024-2025 | 903/BD-I | 06/06/2024 | 01/01/2025 | SUMAN ENTERPRISE AND SUMAN AQUA | 40.09 | 25.37 | 63.29 | 85
11 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . | SM/18529 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Bishnupur Zone-I ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer |  | ORD/000001/2025-2026 | 506/BD-I | 03/04/2025 | 28/01/2026 | NATIONAL CONSTRUCTION | 122.54 | 0 | 0 | 90
Total | [13 empty] | 1478.02 | 394.36 | 26.68