## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | JE_Pravin Kumar Gupta | ORD/000190/2023-2024 | 538/BD-I | 27/07/2023 | 06/08/2023 | TECHVISION | 2.87 | 0 | 0 | 100
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 201/BD-1/6 | 10/02/2024 | 10/02/2024 | Resource Division | 48.66 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Augmentation of Ramnachandpur Zone-II Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Swapna in Nawda Block of Murshidabad District under Berhampore Division-I, PHE. Dte. | Assistant Engineer-II | JE | ORD/000130/2023-2024 | 608/BD-I | 02/08/2023 | 23/08/2026 | KAMIRUL SK AND CO. | 583.11 | 0 | 0 | 80
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Laying of UPVC pipeline at damaged portion of distribution system and rising main pipe line (CI/DI/UPVC) of Ramnachandpur Zone-II water supply scheme under Berhampore Division-I,PHE Dte. For Augmentation of PWSS under Jal Jeevan Mission. | Assistant Engineer-II | JE | ORD/000384/2023-2024 | 140/BD-I | 01/02/2024 | 01/04/2024 | SO-FINE AQUARIUM | 4.62 | 0 | 0 | 100
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ramnachandpur Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | Assistant Engineer-II | JE | ORD/000390/2023-2024 | 153/BD-I | 05/02/2024 | 07/10/2024 | INDRAJIT MAZUMDER | 18 | 0 | 0 | 90
Total | [13 empty] | 657.26 | 0 | 0