## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | JE_Pravin Kumar Gupta | ORD/000190/2023-2024 | 538/BD-I | 27/07/2023 | 06/08/2023 | TECHVISION | 2.87 | 2.87 | 100 | 100
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 201/BD-1/6 | 10/02/2024 | 10/02/2024 | Resource Division | 48.66 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Laying of UPVC pipeline at damaged portion of distribution system and rising main pipe line (CI/DI/UPVC) of Ramnachandpur Zone-II water supply scheme under Berhampore Division-I,PHE Dte. For Augmentation of PWSS under Jal Jeevan Mission. | Assistant Engineer-II | JE | ORD/000384/2023-2024 | 140/BD-I | 01/02/2024 | 01/04/2024 | SO-FINE AQUARIUM | 4.62 | 4.2 | 90.94 | 100
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ramnachandpur Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | Assistant Engineer-II | JE | ORD/000390/2023-2024 | 153/BD-I | 05/02/2024 | 07/10/2024 | INDRAJIT MAZUMDER | 18 | 3.86 | 21.43 | 90
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 79 Cum/hr.) with allied work at Ramnachandrapur Zone-II Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | Assistant Engineer-II | JE | ORD/000014/2024-2025 | 915/BD-I | 07/06/2024 | 07/07/2024 | J.S. CONSTRUCTION | 25.84 | 25.42 | 98.4 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Improvement of OHR (350 Cum) Extension of Boundary Wall & Service Road for Augmentation of Ramnachandpur Zone-II PWSS within Nawda block under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer-II | JE | ORD/000056/2024-2025 | 1127/BD-I | 11/07/2024 | 30/01/2025 | TITLI ENTERPRISE | 15.58 | 4.01 | 25.71 | 90
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Balance work i.c.w. Improvement of Existing AIRP of (Capacity 79 Cum/hr.) with allied works at Ramnachandpur Zone-II Water Supply Scheme under Jal Jeevan Mission within Nawda block under Berhampore Division-I, PHE Dte. In the district of Murshidabad. | Assistant Engineer-II | JE | ORD/000059/2025-2026 | 771/BD-I | 22/05/2025 | 21/06/2025 | J.S. CONSTRUCTION | 17.81 | 0 | 0 | 100
Total | [13 empty] | 133.38 | 40.36 | 30.26