## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | JE_Pravin Kumar Gupta | ORD/000190/2023-2024 | 538/BD-I | 27/07/2023 | 06/08/2023 | TECHVISION | 2.87 | 2.87 | 100 | 100
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , Zone-II under RAMNACHANDPUR ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001429/2023-2024 | 4319/MEDB | 29/12/2023 | 28/03/2024 | JAL PRAVAHIKA PVT LTD | 35.21 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 201/BD-1/6 | 10/02/2024 |  | Resource Division | 48.66 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Laying of UPVC pipeline at damaged portion of distribution system and rising main pipe line (CI/DI/UPVC) of Ramnachandpur Zone-II water supply scheme under Berhampore Division-I,PHE Dte. For Augmentation of PWSS under Jal Jeevan Mission. | Assistant Engineer-II | JE | ORD/000384/2023-2024 | 140/BD-I | 01/02/2024 | 01/04/2024 | SO-FINE AQUARIUM | 4.62 | 2.1 | 45.47 | 100
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ramnachandpur Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | Assistant Engineer-II | JE | ORD/000390/2023-2024 | 153/BD-I | 05/02/2024 | 06/03/2024 | INDRAJIT MAZUMDER | 18 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Augmentation of Ramnachandpur Zone-II Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Swapna in Nawda Block of Murshidabad District under Berhampore Division-I, PHE. Dte. | Assistant Engineer-II | JE | ORD/000130/2023-2024 | 608/BD-I | 02/08/2023 | 01/08/2024 | KAMIRUL SK AND CO. | 583.11 | 33.88 | 5.81 | 15
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Improvement of OHR (350 Cum) Extension of Boundary Wall & Service Road for Augmentation of Ramnachandpur Zone-II PWSS within Nawda block under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer-II |  | ORD/000056/2024-2025 | 1127/BD-I | 11/07/2024 | 09/09/2024 | TITLI ENTERPRISE | 15.58 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . | SM/18536 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 79 Cum/hr.) with allied work at Ramnachandrapur Zone-II Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | Assistant Engineer-II | JE | ORD/000014/2024-2025 | 915/BD-I | 07/06/2024 | 07/07/2024 | J.S. CONSTRUCTION | 25.84 | 0 | 0 | 100
Total | [13 empty] | 733.89 | 38.85 | 5.29