## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS | SM/18579 | New | PAIKPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer |  | ORD/000342/2023-2024 | 1256/BD-I | 22/12/2023 | 21/03/2024 | SATELLITE CONSTRUCTION | 67.11 | 0 | 0 | 0
2 | MURSHIDABAD | Lalgola | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS | SM/18579 | New | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 304/BD-1/3 | 22/02/2024 | 22/02/2024 | Resource Division | 27.92 | 0 | 0 | 0
3 | MURSHIDABAD | Lalgola | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS | SM/18579 | New | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 201/BD-1/28 | 10/02/2024 | 10/02/2024 | Resource Division | 66.86 | 0 | 0 | 0
4 | MURSHIDABAD | Lalgola | Berhampore Mechanical | PAIKPARA AND ADJOINING MOUJAS PWSS | SM/18579 | New | PAIKPARA PH-1 |  |  | BILL/01518/2023-2024 | 387/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 3.3 | 0 | 0 | 0
5 | MURSHIDABAD | Lalgola | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS | SM/18579 | New | PAIKPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer | JE | ORD/000144/2023-2024 | 631/BD-I | 04/08/2023 | 31/03/2026 | H.I ENTERPRISE | 440.19 | 188.98 | 42.93 | 17
6 | MURSHIDABAD | Lalgola | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS | SM/18579 | New | PAIKPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer | JE | ORD/000146/2023-2024 | 633/BD-I | 04/08/2023 | 31/01/2024 | NIRMAL UDYOG | 116.86 | 25.85 | 22.13 | 20
7 | MURSHIDABAD | Lalgola | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS | SM/18579 | New | PAIKPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer | JE | ORD/000145/2023-2024 | 632/BD-I | 04/08/2023 | 24/07/2025 | SRIJON ENTERPRISE | 240.5 | 148.76 | 61.85 | 15
8 | MURSHIDABAD | Lalgola | Central Drilling | PAIKPARA AND ADJOINING MOUJAS PWSS | SM/18579 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 7.79 | 1.08 | 20
9 | MURSHIDABAD | Lalgola | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS | SM/18579 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PAIKPARA Water Supply Scheme(2nd & 3rd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer |  | ORD/000328/2024-2025 | 274/BD-I | 11/02/2025 | 13/03/2025 | NADIA TUBEWELLS | 17.99 | 0 | 0 | 0
Total | [13 empty] | 1700.96 | 371.38 | 21.83