## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Beldanga-II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | GHOLLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer-II | JE | ORD/000164/2023-2024 | 647/BD-I | 08/08/2023 | 04/02/2024 | M/S JHA CONSTRUCTION | 180.62 | 0 | 0 | 0
2 | MURSHIDABAD | Beldanga-II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 201/BD-1/1 | 10/02/2024 | 10/02/2024 | Resource Division | 25 | 0 | 0 | 0
3 | MURSHIDABAD | Beldanga-II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 2096/BD-I/1 | 25/11/2024 | 25/11/2024 | Resource Division | 29.76 | 0 | 0 | 0
4 | MURSHIDABAD | Beldanga-II | Berhampore Mechanical | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | NEW CONNECTION AT GHOLLA PH-I |  |  | BILL/00172/2024-2025 | 14/WBSEDCL-JJM | 16/04/2024 | 16/04/2024 | WBSEDCL | 5.35 | 0 | 0 | 0
5 | MURSHIDABAD | Beldanga-II | Central Drilling | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | MURSHIDABAD | Beldanga-II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | GHOLLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000150/2023-2024 | 660/BD-I | 08/08/2023 | 07/08/2025 | GITA CONSTRUCTION | 69.92 | 0 | 0 | 40
7 | MURSHIDABAD | Beldanga-II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | GHOLLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-II | JE | ORD/000163/2023-2024 | 648/BD-I | 08/08/2023 | 27/06/2025 | HARAPRASAD DAS | 118.61 | 0 | 0 | 65
8 | MURSHIDABAD | Beldanga-II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | GHOLLA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART A) | Assistant Engineer-II | JE | ORD/000165/2023-2024 | 649/BD-I | 08/08/2023 | 01/06/2026 | RAJ KUMAR MONDAL | 404.58 | 0 | 0 | 50
9 | MURSHIDABAD | Beldanga-II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Allied works for upgradation ,Improvement and laying of "GHOLLA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART A)". | Assistant Engineer-II | JE | ORD/000156/2024-2025 | 1644/BD-I | 23/10/2024 | 03/06/2025 | GITA CONSTRUCTION | 16.79 | 0 | 0 | 90
10 | MURSHIDABAD | Beldanga-II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Gholla" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-119 Cum/hr.) Type-1 - Fully Gravity System with RG Filter | Assistant Engineer-II | JE | ORD/000035/2024-2025 | 999/BD-I | 20/06/2024 | 20/06/2026 | M/S GOUTAM CHAKRABORTY | 272.44 | 0 | 0 | 0
11 | MURSHIDABAD | Beldanga-II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHOLLA PWSS (3rd TW Site) under Jal Jeevan Mission in Beldanga-II Block under Berhampore Division-I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | Assistant Engineer-II |  | ORD/000383/2024-2025 | 445/BD-I | 20/03/2025 | 04/04/2025 | MARUTI CONSTRUCTION & CO. | 9.01 | 0 | 0 | 0
12 | MURSHIDABAD | Beldanga-II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of GHOLLA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000022/2025-2026 | 639/BD-I | 25/04/2025 | 24/06/2025 | SAIF TRADERS | 19 | 0 | 0 | 0
13 | MURSHIDABAD | Beldanga-II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Fabrication and errection of Display Board including vinyl pasting ( 1.80 x 1.20 mtr) of scheme information by using logo and tag line of Jal Jevan Mission at different work sites in the district of Murshidabad under Berhampore Division-I,PHE Dte. | Assistant Engineer-I | Junior Engineer | ORD/000446/2023-2024 | 446/BD-I | 15/03/2024 | 04/04/2024 | SUMAN ENTERPRISE AND SUMAN AQUA | 7.18 | 0 | 0 | 100
Total | [13 empty] | 22498.03 | 0 | 0