## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASHIPUR ZONE-I Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | JE_Pravin Kumar Gupta | ORD/000189/2023-2024 | 531/BD-I | 27/07/2023 | 06/08/2023 | TECHVISION | 2.87 | 2.87 | 100 | 100
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 201/BD-1/7 | 10/02/2024 | 10/02/2024 | Resource Division | 101.3 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | NEW CONNECTION AT KASHIPUR Z-I PH-I |  |  | BILL/01578/2023-2024 | 409/WBSEDCL-JJM | 06/03/2024 | 06/03/2024 | WBSEDCL | 5.27 | 0 | 0 | 0
4 | MURSHIDABAD |  | Central Drilling | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | Augmentation of Kashipur Zone-I Piped water supply scheme to accommodate construction of laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | JE,Junior Engineer-I | ORD/000161/2023-2024 | 668/BD-I | 09/08/2023 | 25/01/2026 | MAMON ENTERPRISE AND CONSTRUCTION | 236.94 | 202.92 | 85.64 | 35
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 126 Cum/hr.) with allied work at Kashipur Zone-I Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | Assistant Engineer-II | JE | ORD/000068/2024-2025 | 1206/BD-I | 26/07/2024 | 22/05/2025 | M/S SAJAHAN CHOWDHURY | 35.07 | 0 | 0 | 80
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of KASHIPUR ZONE-I" ground water supply scheme in BELDANGA-II Block, under Berhampore Division-I, P.H.E Dte(Capacity-30.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | Assistant Engineer-II | JE | ORD/000032/2024-2025 | 995/BD-I | 20/06/2024 | 20/06/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 143.92 | 0 | 0 | 60
8 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | KASHIPUR ZONE-I PROPOSED PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000061/2024-2025 | 1176/BD-I | 25/07/2024 | 21/01/2025 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 20.39 | 0 | 0 | 100
9 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KASHIPUR ZONE-I (PART-B) Water Supply Scheme (TW-I & II Site) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | Assistant Engineer-II | JE | ORD/000293/2024-2025 | 99/BD-I | 20/01/2025 | 17/09/2025 | SUJIT KUMAR SAHA | 18.02 | 0 | 0 | 100
10 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of KASHIPUR ZONE-I (Part-B) PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000041/2025-2026 | 722/BD-I | 15/05/2025 | 14/07/2025 | PRAVAT KUMAR GHOSH | 19 | 0 | 0 | 0
11 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | Construction of Boundary wall at 2nd & 3rd Tube Well Site of KASHIPUR ZONE -I PWSS(Part-A) under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000043/2025-2026 | 725/BD-I | 15/05/2025 | 14/07/2025 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 19.02 | 0 | 0 | 0
12 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | Balance work for Improvement Existing AIRP of (Capacity 126 Cum/hr) with allied work at Kashipur Zone-I water supply scheme under JJM within Beldanga-II under Berhampore Division-I, PHE Dte. In the district of Murshidabad. | Assistant Engineer-II |  | ORD/000056/2025-2026 | 768/BD-I | 22/05/2025 | 06/07/2025 | M/S SAJAHAN CHOWDHURY | 58.23 | 0 | 0 | 0
13 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. | SM/18602 | Augmentation | Balance work for Laying of distribution pipeline of Kashipur Zone-I and allied works under JJM within Beldanga-II Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000081/2025-2026 | 848/BD-I | 23/06/2025 | 21/09/2025 | SOUNAK ENTERPRISE | 84.84 | 0 | 0 | 0
Total | [13 empty] | 22084.64 | 205.8 | 0.93