## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Central Drilling | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 14.52 | 0.07 | 11
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | Augmentation | Augmentation of Rampara Faridpur Piped water supply scheme to accommodate construction of OHR ,Arsenic cum Iron Removal Plant(AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga -II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-II | JE | ORD/000288/2023-2024 | 1017/BD-I | 31/10/2023 | 07/11/2026 | SANJAY BISWAS | 558.97 | 10.45 | 1.87 | 75
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMPARA FORIDPUR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | JE_Pravin Kumar Gupta | ORD/000191/2023-2024 | 720/BD-I | 14/08/2023 | 24/08/2023 | TECHVISION | 2.81 | 2.81 | 100 | 100
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | Augmentation | RAMPARA FARIDPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000456/2023-2024 | 460/BD-I | 15/03/2024 | 08/07/2025 | SAHA CONSTRUCTION | 22.63 | 0 | 0 | 75
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Rampara Faridpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte | Assistant Engineer-II | JE | ORD/000253/2024-2025 | 2249/BD-I | 10/12/2024 | 09/01/2025 | M/S B.R. SUPPLIERS | 9 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | Augmentation | Improvement of existing Pump House & Construction of New Boundary Wall (2nd Site) for Augmentation of Rampara Faridpur PWSS within Beldanga-II under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad | Assistant Engineer-II | JE | ORD/000049/2024-2025 | 1111/BD-I | 10/07/2024 | 08/09/2024 | ABA CONTRACTOR | 12.06 | 3.18 | 26.38 | 100
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 201/BD-1/8 | 10/02/2024 | 10/02/2024 | Resource Division | 36.69 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | Augmentation | NEW CONNECTION AT RAMPARA FARIDPUR PH-1 |  |  | BILL/00615/2024-2025 | 182/WBSEDCL-JJM | 09/08/2024 | 09/08/2024 | WBSEDCL | 3.66 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | Augmentation | RAMPARA FARIDPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, under Jal Jeevan Mission within BELDANGA-II Block in the district of Murshidabad under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II |  | ORD/000382/2024-2025 | 444/BD-I | 20/03/2025 | 04/05/2025 | DATA ENTERPRISE | 9.84 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | Augmentation | Improvement of Existing AIRP (Capacity 68 Cum/hr.) with allied work at Rampara Faridpur (Zone-I) Water Supply Scheme under Jal Jeevan Mission within Beldanga - II under Berhampore Division-I, P.H.Engineering Dte. In the district of Murshidabad. | Assistant Engineer-II |  | ORD/000050/2025-2026 | 759/BD-I | 22/05/2025 | 21/06/2025 | SANJAY BISWAS | 27.45 | 0 | 0 | 0
11 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. | SM/18603 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of RAMPARA FARIDPUR ZONE - II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000021/2025-2026 | 638/BD-I | 25/04/2025 | 24/06/2025 | MASTER CONSTRUCTION | 18.98 | 0 | 0 | 0
Total | [13 empty] | 22041.85 | 30.96 | 0.14