## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS | SM/18690 | New | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 201/BD-1/4 | 10/02/2024 | 10/02/2024 | Resource Division | 12.11 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola-II | Berhampore Mechanical | KHAMARDIAR AND ADJOINING MOUJAS PWSS | SM/18690 | New | NEW CONNECTION AT KHAMARDIAR PH-I |  |  | BILL/00247/2024-2025 | 100/WBSEDCL-JJM | 05/06/2024 | 05/06/2024 | WBSEDCL | 3.37 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS | SM/18690 | New | KHAMARDIAR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000175/2023-2024 | 690/BD-I | 10/08/2023 | 06/02/2024 | SARAJIT KUMAR MAJUMDAR | 289.91 | 209.31 | 72.2 | 60
4 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS | SM/18690 | New | KHAMARDIAR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000176/2023-2024 | 689/BD-I | 10/08/2023 | 16/04/2026 | MD MAIDUL ISLAM | 330.82 | 112.73 | 34.08 | 65
5 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS | SM/18690 | New | KHAMARDIAR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART -C) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000177/2023-2024 | 691/BD-I | 10/08/2023 | 25/07/2026 | M/S BIMALENDU BOSE | 214.12 | 185.32 | 86.55 | 90
6 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS | SM/18690 | New | KHAMARDIAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000187/2023-2024 | 734/BD-I | 16/08/2023 | 14/11/2023 | NATIONAL CONSTRUCTION | 50.37 | 11.84 | 23.5 | 25
7 | MURSHIDABAD | Bhagawangola-II | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS | SM/18690 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Khamardiar Water Supply Scheme under JJM under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-I |  | ORD/000270/2024-2025 | 2331/BD-I | 30/12/2024 | 29/01/2025 | KAMIRUL SK AND CO. | 18.01 | 0 | 0 | 0
8 | MURSHIDABAD | Bhagawangola-II | Central Drilling | KHAMARDIAR AND ADJOINING MOUJAS PWSS | SM/18690 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 0 | 20
Total | [13 empty] | 1638.94 | 519.2 | 31.68