## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | New | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 304/BD-1/1 | 22/02/2024 | 22/02/2024 | Resource Division | 21.31 | 0 | 0 | 0
2 | MURSHIDABAD | Lalgola | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | New | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 201/BD-1/27 | 10/02/2024 | 10/02/2024 | Resource Division | 34.21 | 0 | 0 | 0
3 | MURSHIDABAD | Lalgola | Berhampore Mechanical | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | New | NEW CONNECTION AT KRISHNAPUR DINURPARA PH-1 |  |  | BILL/00666/2024-2025 |  | 03/09/2024 | 03/09/2024 | WBSEDCL | 3.4 | 0 | 0 | 0
4 | MURSHIDABAD | Lalgola | Berhampore Mechanical | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR DINURPARA PUMP HOUSE III , BLOCK - LALGOLA , DISTRICT - MURSHIDABAD. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000024/2025-2026 | 1153/MEDB | 14/05/2025 | 14/08/2025 | DAS ENTERPRISE (CHOA) | 11.82 | 0 | 0 | 0
5 | MURSHIDABAD | Lalgola | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | New | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000168/2023-2024 | 654/BD-I | 08/08/2023 | 07/02/2025 | ULTRA CONSTRUCTION | 91.86 | 0 | 0 | 50
6 | MURSHIDABAD | Lalgola | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | New | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000167/2023-2024 | 653/BD-I | 08/08/2023 | 31/03/2025 | SOUMYADIP MISRA | 326.54 | 0 | 0 | 10
7 | MURSHIDABAD | Lalgola | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | New | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer,Assistant Engineer-I,Assistant Engineer-II | JE | ORD/000166/2023-2024 | 652/BD-I | 08/08/2023 | 03/06/2026 | M/S GOUTAM CHAKRABORTY | 232.47 | 72.29 | 31.1 | 10
8 | MURSHIDABAD | Lalgola | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | New | KRISHNAPURDINURPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000186/2023-2024 | 730/BD-I | 16/08/2023 | 14/11/2023 | M/S SWAPAN KUAMR NATH & CO | 72.82 | 21.2 | 29.11 | 41
9 | MURSHIDABAD | Lalgola | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS | SM/18695 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KRISHNAPUR DINURPARA PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidbad. | Assistant Engineer |  | ORD/000015/2025-2026 | 604/BD-I | 22/04/2025 | 07/05/2025 | M/S BIMALENDU BOSE | 9.01 | 0 | 0 | 0
Total | [13 empty] | 803.44 | 93.49 | 11.64