## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Providing Vertical clear water pumping machinery atop extended Steel structure for feeding newly add Zone-I B and Zone-II B of Augmentation at Beniagram Surface Water Based water supply scheme. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000327/2024-2025 | 2596/MEDB | 30/09/2024 | 31/03/2025 | B. T. PROJECTS PVT. LTD. | 88.81 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 1341/BD-I/1 | 20/08/2024 | 20/08/2024 | Resource Division | 89.82 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 194/BD-I/1 | 09/02/2024 | 09/02/2024 | Resource Division | 89.82 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Wayleave Facility Charge FOR Laying of 600MM Dia. Casing Pipe FOR Passing of 350MM Dia. Carrier Water Pipeline B/W KM-254/2-254/3 Between Station Ballalpur-New Farakka under Malda Division of Eastern Railway. |  |  | BILL/00296/2024-2025 | BP-2024-25-207 | 03/10/2024 | 03/10/2024 | EASTERN RAILWAY MALDA DIVISION | 5.35 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Sundarpur ground water supply scheme in Bhagwabgola-I Block, Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000013/2025-2026 | 1138/MEDB | 13/05/2025 | 13/08/2025 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 39.58 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Augmentation of Beniagram Surface water based water supply scheme to accommodate construction of OHR, pump house and boundary wall, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Farakka Block of Murshidabad District under Berhampore Division-I,PHE.Dte. in the district Murshidabad. | Assistant Engineer | JE,Junior Engineer-I | ORD/000200/2023-2024 | 841/BD-I | 05/09/2023 | 04/09/2024 | CHAKRABORTY CONSTRUCTION | 3038.97 | 305.29 | 10.05 | 50
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Augmentation of different units of WTP premises of Beniagram Water Supply scheme under, Berhampore Division -I PHE.Dte. under JJM | Assistant Engineer | Junior Engineer-I | ORD/000024/2024-2025 | 945/BD-I | 11/06/2024 | 10/08/2024 | P.M CONSTRUCTION | 97.98 | 17.2 | 17.55 | 25
Total | [13 empty] | 3450.34 | 322.48 | 9.35