## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Providing Vertical clear water pumping machinery atop extended Steel structure for feeding newly add Zone-I B and Zone-II B of Augmentation at Beniagram Surface Water Based water supply scheme. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000327/2024-2025 | 2596/MEDB | 30/09/2024 | 31/03/2025 | B. T. PROJECTS PVT. LTD. | 88.81 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 1341/BD-I/1 | 20/08/2024 | 20/08/2024 | Resource Division | 89.82 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 194/BD-I/1 | 09/02/2024 | 09/02/2024 | Resource Division | 89.82 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Wayleave Facility Charge FOR Laying of 600MM Dia. Casing Pipe FOR Passing of 350MM Dia. Carrier Water Pipeline B/W KM-254/2-254/3 Between Station Ballalpur-New Farakka under Malda Division of Eastern Railway. |  |  | BILL/00296/2024-2025 | BP-2024-25-207 | 03/10/2024 | 03/10/2024 | EASTERN RAILWAY MALDA DIVISION | 5.35 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Sundarpur ground water supply scheme in Bhagwabgola-I Block, Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000013/2025-2026 | 1138/MEDB | 13/05/2025 | 13/08/2025 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 39.58 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Augmentation of Beniagram Surface water based water supply scheme to accommodate construction of OHR, pump house and boundary wall, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Farakka Block of Murshidabad District under Berhampore Division-I,PHE.Dte. in the district Murshidabad. | Assistant Engineer | JE,Junior Engineer-I | ORD/000200/2023-2024 | 841/BD-I | 05/09/2023 | 04/09/2024 | CHAKRABORTY CONSTRUCTION | 3038.97 | 305.29 | 10.05 | 50
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Augmentation of different units of WTP premises of Beniagram Water Supply scheme under, Berhampore Division -I PHE.Dte. under JJM | Assistant Engineer | Junior Engineer-I | ORD/000024/2024-2025 | 945/BD-I | 11/06/2024 | 10/08/2024 | P.M CONSTRUCTION | 97.98 | 17.2 | 17.55 | 25
8 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Repair and overhauling at filter beds including supply and filling of filter media alongwith allied works at R.G filter bed of Beniagram Surface Water Based water supply scheme in Farrakka block under Raghunathganj Sub division under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer | Junior Engineer-I | ORD/000204/2023-2024 | 849/BD-I | 05/09/2023 | 05/10/2023 | P.M CONSTRUCTION | 21.01 | 21.01 | 100 | 10
9 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME | SM/18699 | Augmentation | Rejuvenation of of 7.8 MLD Capacity Water Treatment Plant (Inlet well ,Flush Mixture ,Clarifoculator, Chemical Dosing and Filter House ) at Beniagram Under Berhampore Division - I , In The District Murshidabad , PHE Dte . | Assistant Engineer | Junior Engineer-I | ORD/000382/2023-2024 | 117/BD-I | 30/01/2024 | 30/03/2024 | P.M CONSTRUCTION | 144.24 | 137.72 | 95.48 | 10
Total | [13 empty] | 3615.59 | 481.21 | 13.31