## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Beldanga-II | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | New | PALITPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer-II |  | ORD/000178/2023-2024 | 688/BD-I | 10/08/2023 | 06/02/2024 | M/S AMIT KUMAR GUPTA | 167.04 | 0 | 0 | 0
2 | MURSHIDABAD | Beldanga-II | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | New | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 201/BD-1/2 | 10/02/2024 | 10/02/2024 | Resource Division | 56.21 | 0 | 0 | 0
3 | MURSHIDABAD | Beldanga-II | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | New | Material Requisition To Resource Division |  |  | RTOR000022/2024-2025 | 2096/BD-I/3 | 25/11/2024 | 25/11/2024 | Resource Division | 27.02 | 0 | 0 | 0
4 | MURSHIDABAD | Beldanga-II | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | New | PALITPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-II |  | ORD/000174/2023-2024 | 687/BD-I | 10/08/2023 | 06/02/2024 | BANIK BROTHERS | 89.01 | 0 | 0 | 0
5 | MURSHIDABAD | Beldanga-II | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | New | PALITPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer-II | JE | ORD/000173/2023-2024 | 686/BD-I | 10/08/2023 | 09/08/2025 | SUJIT KUMAR SAHA | 401.71 | 91.16 | 22.69 | 55
6 | MURSHIDABAD | Beldanga-II | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | New | PALITPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000188/2023-2024 | 736/BD-I | 16/08/2023 | 01/08/2025 | S.K CONSTRUCTION (SUDIP KUMAR SANYAL) | 72.82 | 12.05 | 16.54 | 40
7 | MURSHIDABAD | Beldanga-II | Central Drilling | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | New | Hiring of Diesel Driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Mech./Elect. Planning Wing, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000013/2024-2025 | 136/S&WSD | 24/06/2024 | 25/12/2024 | NEMAI CHANDRA NAIYA | 0.87 | 2.06 | 236.22 | 0
8 | MURSHIDABAD | Beldanga-II | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Palitpara" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-111 Cum/hr.) Type-1 - Fully Gravity System with RG Filter | Assistant Engineer-II | JE | ORD/000034/2024-2025 | 998/BD-I | 20/06/2024 | 20/06/2026 | M/S GOUTAM CHAKRABORTY | 257.77 | 0 | 0 | 0
9 | MURSHIDABAD | Beldanga-II | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | New | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of PALITPARA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000009/2025-2026 | 596/BD-I | 22/04/2025 | 21/06/2025 | S.K CONSTRUCTION (SUDIP KUMAR SANYAL) | 19 | 0 | 0 | 0
10 | MURSHIDABAD | Beldanga-II | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | New | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of PALITPARA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000037/2025-2026 | 666/BD-I | 29/04/2025 | 28/06/2025 | INDIAN TRADING CORPORATION | 19 | 0 | 0 | 0
11 | MURSHIDABAD | Beldanga-II | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS | SM/18709 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PALITPARA Water Supply Scheme (TW - II & III Site) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-II | JE | ORD/000282/2024-2025 | 14/BD-I | 06/01/2025 | 06/05/2025 | SARKAR WATER SUPPLY AGENCY | 18 | 0 | 0 | 100
Total | [13 empty] | 1128.47 | 105.27 | 9.33