## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Providing Electrical Equipment for 11/0.433 KV Sub-station (LT Bulk & HT Bulk) at Intake and Water Treatment Plant under Augmentation of Central Sector, Part-I Surface Water Based W/S Scheme, Dist. Murshidabad | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001569/2023-2024 | 973/MEDB | 15/03/2024 | 15/09/2024 | CONCORD ENGINEERING | 239.82 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 790/BD-I | 09/05/2024 | 09/05/2024 | Resource Division | 478.82 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 1341/BD-I/2 | 20/08/2024 | 20/08/2024 | Resource Division | 387.17 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 1462/BD-I | 05/09/2024 | 05/09/2024 | Resource Division | 123.2 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 1148/BD-I | 18/07/2024 | 18/07/2024 | Resource Division | 817.87 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 1412/BD-I | 30/08/2024 | 30/08/2024 | Resource Division | 1050.72 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | SHIFTING OF DTR 25KVA AT MANIKNAGAR CID 860311628 |  |  | BILL/00663/2024-2025 |  | 03/09/2024 | 03/09/2024 | WBSEDCL | 0.71 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Safety Checking of 9 (Nine) nos Over Head Reservoit at various places of Murshidabad District under P.H.Engineering Department, Govt of West Bengal. |  |  | BILL/00347/2024-2025 | BP-2024-25-259 | 27/11/2024 | 27/11/2024 | SRCC NIT DURGAPUR | 3.54 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Rejuvanation of of 30.33 MLD Capacity Water Treatment Plant (Inlet well ,Flush Mixture ,Clarifoculator , Chemical Dosing and Filter House ) at Central Sector Part- I (At Lalbagh) Under Berhampore Division - I , In The District Murshidabad , PHE Dte . | Assistant Engineer-I | Junior Engineer-I | ORD/000437/2023-2024 | 391/BD-I | 12/03/2024 | 03/09/2025 | DHIMAN SARKAR | 270.68 | 0 | 0 | 80
10 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | EXECUTION OF CLEAR WATER RISING MAIN, OVERHEAD RESERVOIRS WITH ALLIED WORKS, DISTRIBUTION NETWORK WITH FHTC COMPLETE FOR AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CENTRAL SECTOR PART-I OF MURSHIDABAD DISTRICT | Assistant Engineer-I | JE,Junior Engineer-I | ORD/000435/2023-2024 | 387/BD-I | 12/03/2024 | 09/07/2026 | M/S MOHAN LAL JAIN | 7952.07 | 1331.31 | 16.74 | 60
11 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Withdrawing and Laying of different dia. D.I. pipe along NH12 from Bhakuri to Talbagan more with connection work to Rising Mains of Central Sector Part-II near Bhakuri more and Balarampur Halt Station under Berhampore Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000120/2024-2025 | 1469/BD-I | 06/09/2024 | 04/05/2025 | SAMBHUNATH ROY | 53.6 | 0 | 0 | 80
12 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer-II,BD-I,PHE Dte. [Period for 05.07.2024 to 30.06.2025.] Car No-WB58CC 9776 | Assistant Engineer-II | JE | ORD/000046/2024-2025 | 1082/BD-I | 04/07/2024 | 04/07/2025 | MD MUKLESUR RAHAMAN | 1.81 | 4.79 | 264.06 | 0
13 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Allied Work for Supply of different types of specials in connection with execution of Clear Water Rising Main, Overhead Reservoirs, Distribution Network Complete under JJM for Augmentation of Surface Water Based Piped Water Supply Scheme of CENTRAL SECTOR PART-II under BERHAMPORE DIVISION - I in the district of MURSHIDABAD | Assistant Engineer-II |  | ORD/000266/2024-2025 | 2324/BD-I | 26/12/2024 | 25/01/2025 | ECO PROTECTION ENGINEERS PVT LTD. | 35.3 | 0 | 0 | 0
14 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | EXECUTION OF CLEAR WATER RISING MAIN, OVERHEAD RESERVOIRS WITH ALLIED WORKS, DISTRIBUTION NETWORK WITH FHTC COMPLETE FOR AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CENTRAL SECTOR PART-II OF MURSHIDABAD DISTRICT | Assistant Engineer-II | JE | ORD/000436/2023-2024 | 388/BD-I | 12/03/2024 | 01/08/2026 | ECO PROTECTION ENGINEERS PVT LTD. | 16059.7 | 808.08 | 5.03 | 35
15 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Survey, Investigation, Planning, Design, Execution commissioning and completion in all respect of all Civil, Electrical and Mechanical work of 11 MLD capacity conventional water treatment plant (WTP) using River Bhagirathi as source including Intake Structures, Raw Water rising main, and Clear Water rising main upto boundary limit of WTP for the Augmentation of surface water based piped water supply scheme for Murshidabad Central Sector (Part-I) in Murshidabad District under PHE Dte. including 12 (Twelve) months of Operation and Maintenance after successful completion of 3 (Three) months Trial Run | Assistant Engineer-II | Junior Engineer-I | ORD/000434/2023-2024 | 386/BD-I | 12/03/2024 | 12/09/2025 | CONCORD ENGINEERING | 3354.92 | 0 | 0 | 0
16 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Rejuvanation of 54.11 MLD Capacity Water Treatment Plant (Inlet well ,Flush Mixture,Clarifoculator, Chemical Dosing and Filter House ) at Central Sector Part-II UNDER BERHAMPORE DIVISION - I , IN THE DISTRICT MURSHIDABAD , PHE DTE . | Assistant Engineer-II | JE | ORD/000432/2023-2024 | 385/BD-I | 12/03/2024 | 02/07/2025 | CONCORD ENGINEERING | 296.54 | 0 | 0 | 60
17 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Allied Work for Supply of different types of specials in connection with execution of Clear Water Rising Main, Overhead Reservoirs, Distribution Network Complete under JJM for Augmentation of Surface Water Based Piped Water Supply Scheme of CENTRAL SECTOR PART-I under BERHAMPORE DIVISION - I in the district of MURSHIDABAD. | Assistant Engineer-I |  | ORD/000256/2024-2025 | 2269/BD-I | 16/12/2024 | 15/01/2025 | M/S MOHAN LAL JAIN | 36.33 | 0 | 0 | 0
18 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Renovation and upgradation of all existing infrastructures (Filter House Building,Chemical House Building,Laboratory/SCADA Building,Clear Water Pump House, Clear Water Reservoir, Outhouse, Staff Quarters and allied Works) of Augumentation of Central Sector Part-II under JJM under Berhampore Division-I, P.H.E Dte. | Assistant Engineer-II |  | ORD/000272/2024-2025 | 2334/BD-I | 30/12/2024 | 13/02/2025 | CONCORD ENGINEERING | 59.47 | 0 | 0 | 0
19 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Improvement of existing Pump House & Construction of Boundary Wall at different head work sites for Augmentation of different PWSS within MJ & Berhampore Block under Central Sector Part-I under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer-I | JE | ORD/000142/2024-2025 | 1610/BD-I | 03/10/2024 | 31/05/2025 | M/S J.S ENTERPRISE | 85.47 | 0 | 0 | 40
20 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Renovation and upgradation of all existing infrastructures (Sludge Sump House, Sludge pond, Substation Building,Boundary Wall, Clariflocculator, Flash Mixer, Inlet Well and allied Works) of Augumentation of Central Sector Part-II under JJM under Berhampore Division-I, P.H.E Dte. | Assistant Engineer-II |  | ORD/000271/2024-2025 | 2333/BD-I | 30/12/2024 | 13/02/2025 | CONCORD ENGINEERING | 42.16 | 0 | 0 | 0
21 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Continuation Work order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer-II,BD-I,PHE Dte. [Period for 01.07.2025 to 31.10.2025.] Car No-WB58CC 9776 | Assistant Engineer-II | JE | ORD/000095/2025-2026 | 1082/BD-I | 30/06/2025 | 31/10/2025 | MD MUKLESUR RAHAMAN | 0.6 | 0 | 0 | 0
22 | MURSHIDABAD |  | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) | SM/19189 | Augmentation | Consultancy for Engineering support of six numbers of Suspended OHR constructed in stages initially during 2011-2012 and after 5-6 years gap in Berhampore Division-I of PHE Dte. based on Joint Inspection, Non-destructive Test and subsequent Structural Analysis of their As Built Numerical Models in FEM Platform including Seismic Considerations. | Assistant Engineer-II |  | ORD/000091/2025-2026 | 959/BD-I | 22/07/2025 | 20/09/2025 | JADAVPUR UNIVERSITY | 49.21 | 0 | 0 | 0
Total | [13 empty] | 31399.71 | 2144.18 | 6.83