## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) | SM/06732 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Kendgara Village (JL No.-120) of different locations from existing distribution system within the command area of Khoyrasole Piped Water Supply Scheme at Khoyrasole Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte (Sl. No.-2) | AE | JE2 | ORD/000274/2021-2022 | 1476/BHM | 06/09/2021 | 05/11/2021 | NUR MOBINUL ISLAM | 27.58 | 27.25 | 98.79 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) | SM/06732 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Mahammadpur Village (JL No.-115) of different locations from existing distribution system within the command area of Khoyrasole Piped Water Supply Scheme at Khoyrasole Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte. (Sl. No.21) | AE | JE2 | ORD/000564/2020-2021 | 203/BHM | 18/02/2021 | 04/04/2021 | BHAGYADHAR GHOSH | 14.28 | 12.93 | 90.55 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) | SM/06732 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Churar Village (JL No.-137) of different locations from existing distribution system within the command area of Khoyrasole Piped Water Supply Scheme at Khoyrasole Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte. (Sl. No.-1) | AE | JE,JE1 | ORD/000023/2021-2022 | 1096/BHM | 07/07/2021 | 05/09/2021 | PRAVAT SARKAR | 35.23 | 34.02 | 96.57 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) | SM/06732 | Retrofitting | Supply and delivery of Sluice Valve for Augmentation of Khoyrasole Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-6) | AE(HQ) | JE2 | ORD/000348/2023-2024 | 4625/BHM | 18/12/2023 | 17/01/2024 | BAHIR CONSTRUCTION PRIVATE LIMITED | 9.3 | 9.3 | 100 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) | SM/06732 | Retrofitting | Continuation Work Order for Supply and delivery of Sluice Valve for Augmentation of Khoyrasole Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-6) | AE(HQ) | JE2 | ORD/000579/2023-2024 | 737/BHM | 28/02/2024 | 29/03/2024 | BAHIR CONSTRUCTION PRIVATE LIMITED | 9.3 | 9.3 | 100 | 100
Total | [13 empty] | 95.7 | 92.81 | 96.98