## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS | SM/06734 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 03) | AE | JE3 | ORD/000321/2021-2022 | 353/BSSD | 25/10/2021 | 14/11/2021 | SACHIN KUMAR SARKAR | 3.88 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS | SM/06734 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Malian, Joka & Kamalpur of Tilpara w/s Scheme at Suri-I Block within Suri Sadar Sub Division under Birbhum Division, PHE Dte. (Sl. No.1) | AE | JE3 | ORD/000058/2020-2021 | 1420/BHM | 04/11/2020 | 19/12/2020 | B.M.SARKAR | 17.18 | 29.65 | 172.62 | 97
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS | SM/06734 | Retrofitting | Providing functional house tap connection (FHTC) from existing distribution system within the command area of Tilpara Water Supply Scheme. | AE | JE3 | ORD/000215/2020-2021 | 1707/BHM | 23/12/2020 | 21/02/2021 | RAJ KUMAR DAS | 47.57 | 47.86 | 100.61 | 65
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS | SM/06734 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Araipur of Tilpara w/s Scheme at Suri I Block within Suri Sadar Sub Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.22) | AE | JE3 | ORD/000216/2020-2021 | 1713/BHM | 23/12/2020 | 06/02/2021 | PRANAB KUMAR GHOSH | 21.28 | 37.05 | 174.11 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS | SM/06734 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kalpatarupally under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl.No. -02) | AE | JE3 | ORD/000275/2021-2022 | 336/BSSD | 23/09/2021 | 13/10/2021 | M/S SARADA CONSTRUCTION. | 4.02 | 0 | 0 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS | SM/06734 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 03) | AE | JE3 | ORD/000553/2021-2022 | 353/BSSD. | 25/10/2021 | 14/11/2021 | SACHIN KUMAR SARKAR | 3.88 | 0 | 0 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS | SM/06734 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tilpara w/s Scheme (Left out House Hold) in Suri Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.1) | AE | JE3 | ORD/000257/2021-2022 | 1506/BHM | 09/09/2021 | 08/11/2021 | RAJKUMAR DAS | 39.43 | 0 | 0 | 50
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS | SM/06734 | Retrofitting | Providing Functional Household Tap Connection (FHTC)from existing distribution system in habitaiton of Kamapur Nutunpara under Kamalpur Mouza (Jl. NO.4) under Suri-I Block within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.01) | AE | JE3 | ORD/000002/2021-2022 | 191/BSSD | 02/06/2021 | 22/06/2021 | BAMDEB CONSTRUCTION | 4.92 | 4.91 | 99.87 | 0
Total | [13 empty] | 142.17 | 119.47 | 84.04