## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | SM/06735 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Moldihi, Koma, Kanslpai, Muradpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000620/2020-2021 | 1174/BHM | 21/09/2020 | 20/11/2020 | SYED KHORSID ALAM | 32.84 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | SM/06735 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Moldihi, Koma, Kanslpai, Muradpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000186/2020-2021 | 1174/BHM | 21/09/2020 | 20/11/2020 | SYED KHORSID ALAM | 32.84 | 49.09 | 149.51 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | SM/06735 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Januri, Uttar Metegram, Rajnagar, Shibpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE1 | ORD/000744/2020-2021 | 1281/BHM | 07/10/2020 | 21/11/2020 | NUR MOBINUL ISLAM | 12.08 | 2.62 | 21.68 | 75
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | SM/06735 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Januri, Uttar Metegram, Rajnagar, Shibpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE1 | ORD/000061/2020-2021 | 1282/BHM | 01/10/2020 | 15/11/2020 | ISLAM CONSTRUCTION | 12.08 | 20.07 | 166.18 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | SM/06735 | Retrofitting | Extension of pipe line for Providing Functional Household Tap Connection (FHTC) at Kanspai( JL No. - 82) Muradpur Adibasipara (JL No. 83), Maldihi Adibasipara (JL No.-80) & Khanna (JL No.-) Villages of different locations from existing distribution system within the command area of Chatra-Koma Piped Water Supply Scheme at Suri-II Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte. (Sl. No. - 09) | AE |  | ORD/000608/2020-2021 | 71/BSSD. | 26/02/2021 | 13/03/2021 | SYED KHORSID ALAM | 3.82 | 0 | 0 | 0
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | SM/06735 | Retrofitting | Extension of pipe line for Providing Functional Household Tap Connection (FHTC) at Kanspai (JL No.82) Muradpur Adibasipara (Jl. No.83), Maldihi Adibashipara (Sl. No.80) & Khanna (Jl. No.) Villages of different locations from existing distribution system within the command area of Chatra-Koma Piped Water Supply Scheme at Suri-II Block under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.09) | AE |  | ORD/000381/2020-2021 | 71/ BSSD | 26/02/2021 | 13/03/2021 | SYED KHORSID ALAM | 3.82 | 7.8 | 204.04 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | SM/06735 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chatra-Koma Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. (Sl. No. - 05) | AE | JE1 | ORD/000047/2022-2023 | 91/BSSD | 27/05/2022 | 16/06/2022 | INDRAJIT MONDAL | 4.05 | 3.37 | 83.16 | 92
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) | SM/06735 | Retrofitting | Laying Distribution pipeline from MSK school towards main road under Charta- Coma Piped Water Suply Scheme under Birbhum Sadar Sub Division, P.H.E Dte. within Birbhum Division PHE Dte. | AE | JE1 | ORD/000084/2023-2024 | 1637/BHM | 02/05/2023 | 01/06/2023 | SUBHANKAR ROY | 5.3 | 0 | 0 | 100
Total | [13 empty] | 106.81 | 82.94 | 77.65