## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | SM/06736 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Jamrand Bauripara, Fullaichack & Bartikuri under Jamrand Mouza (JL No. - 136) under Khoyrasole Block, within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 32)) | AE | JE2 | ORD/000012/2021-2022 | 207/BSSD | 15/06/2021 | 15/07/2021 | RICK CONSTRUCTION | 4.97 | 4.97 | 100 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | SM/06736 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Isgara, Narayanpur, Beldanga & Rajnagar in Jamrand w/s Scheme under Suri Sadar Sub Division within Birbhum Division, PHE Dte. (Sl. No.18) | AE | JE2 | ORD/000314/2020-2021 | 1708 /BHM | 23/12/2020 | 21/02/2021 | PRAVAT SARKAR | 29.59 | 50.84 | 171.8 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | SM/06736 | Retrofitting | Relaying of UPVC distribution Pipe line due to damage for construction of drain and reconnection of existing Household Tap Connection (FHTC) from Kendragaria Gram Panchayat Office towards Sarafat Khan house under Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H. E Dte. (Sl. No. - 07) | AE |  | ORD/000985/2021-2022 | 405/BSSD | 14/12/2021 | 29/12/2021 | GOUTAM MONDAL | 1.28 | 1.28 | 99.88 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | SM/06736 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Jamrand Chasapara under Jamrand Mouza (JL No.-136) under Khoyrasole Block,within the command area of Jamrand Piped w/s Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. (SL No.-31) | AE | JE2 | ORD/000014/2021-2022 | 206/BSSD | 15/06/2021 | 15/07/2021 | SUMAN CHOWDHURY | 4.97 | 4.5 | 90.63 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | SM/06736 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Jamrand, Matiala Bhimgara in Jamrand w/s Scheme under Suri Sadar Sub Division within Birbhum Division, PHE Dte. (Sl. No.17) | AE | JE2 | ORD/000278/2020-2021 | 1709/BHM | 23/12/2020 | 21/02/2021 | RICK CONSTRUCTION | 30.49 | 28.94 | 94.92 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | SM/06736 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. (Sl. No. ¿ 01) | AE | JE2 | ORD/000045/2022-2023 | 89/BSSD | 27/05/2022 | 16/06/2022 | SK FAQHRUL AMIN | 4.99 | 4.98 | 99.87 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | SM/06736 | Retrofitting | Restoration of distribution pipe line at various location nearby Kabbarsthan, Bimgarh Bus Stand etc. for smooth running of FHTC under Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte.(Sl. No. - 15) | AE | JE2 | ORD/000514/2022-2023 | 226/BSSD | 21/09/2022 | 11/10/2022 | GOUTAM MONDAL | 4.91 | 4.91 | 99.92 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS | SM/06736 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Beledanga area (J.L :- 142) Habitation of Rathtala under Beledanga Mouza under Suri- Khayrasole Block, within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 07) | AE | JE2 | ORD/000177/2021-2022 | 285/BSSD | 13/08/2021 | 12/09/2021 | B.M.SARKAR | 4.04 | 3.61 | 89.43 | 100
Total | [13 empty] | 85.25 | 104.04 | 122.04