## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | Retrofitting | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Chandpara Habitation of Chandpara Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. | AE | JE3 | ORD/000598/2020-2021 | 287/RSD | 31/12/2020 | 15/01/2021 | ABUL HASNAT | 0.1 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | Retrofitting | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Different places of Mayureswar-I & Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. | AE | JE3 | ORD/000601/2020-2021 | 290/RSD | 31/12/2020 | 15/01/2021 | ABUL HASNAT | 0.07 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | Retrofitting | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Chandpara Habitation of Chandpara Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte | AE | JE3 | ORD/000597/2020-2021 | 286/RSD | 31/12/2020 | 15/01/2021 | ABUL HASNAT | 0.1 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | Retrofitting | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Kamra, Kayemba, Shilgram Habitation of Kamra, Kayemba, Shilgram Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. | AE | JE3 | ORD/000599/2020-2021 | 288/RSD | 31/12/2020 | 15/01/2021 | ABUL HASNAT | 0.09 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | Retrofitting | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Dunigram, Harirampur Habitation of Dunigram Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. | AE | JE3 | ORD/000600/2020-2021 | 289/RSD | 31/12/2020 | 15/01/2021 | ABUL HASNAT | 0.1 | 0 | 0 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | Retrofitting | Providing Tap Connection for Existing School & AWC under Shilogram, Kamra,Kayemba,Chandpara, Harirampur Mouzas in Dunigram PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000076/2021-2022 | 275/RSD | 16/07/2021 | 26/07/2021 | MD ABSAR ALI | 0.99 | 0 | 0 | 50
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | Retrofitting | Laying of Distribution System with UPVC Pipes and Providing Tap Connection for Existing School & AWC under Dunigram Mouza in Dunigram PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000075/2021-2022 | 274/RSD | 16/07/2021 | 26/07/2021 | MD ABSAR ALI | 1 | 0 | 0 | 50
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kayemba, Bara Chauki of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.5) | AE | JE3 | ORD/000047/2020-2021 | 1239/BHM | 28/09/2020 | 27/11/2020 | KAZI EMDADUL HAQUE | 32.58 | 25.18 | 77.27 | 0
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Shigram of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000053/2020-2021 | 1177 /BHM | 21/09/2020 | 20/11/2020 | M/S MD AMINUL ISLAM | 31.84 | 26.3 | 82.62 | 0
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) | SM/06737 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kamra, Harirampur of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.4) | AE | JE3 | ORD/000043/2020-2021 | 1238 /BHM | 28/09/2020 | 12/11/2020 | UMWELT ENGINEER PVT. LTD | 29.57 | 25.51 | 86.26 | 0
Total | [13 empty] | 96.44 | 76.99 | 79.83