## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS | SM/06738 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Uttar Narayanpur, Kurula Ambha of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-A) | AE | JE2 | ORD/000051/2020-2021 | 1178 /BHM | 21/09/2020 | 20/11/2020 | SUNIL RABI DAS | 41.99 | 18.96 | 45.14 | 79
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS | SM/06738 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Mara Basahar, Jagadispur of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-B) | AE | JE2 | ORD/000054/2020-2021 | 1179 /BHM | 21/09/2020 | 20/11/2020 | SANJUKTA ENGINEERS | 32.72 | 26.03 | 79.57 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS | SM/06738 | Retrofitting | Construction of supporting arrangement for Solar pump at Uttar Narayanpur under Rampurhat Sub- division PHE Dte. | AE | JE2 | ORD/000530/2021-2022 | 18/RSD | 04/01/2022 | 03/02/2022 | SHIB GANGA CONSTRUCTION | 1.54 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS | SM/06738 | Retrofitting | Additional Laying of UPVC Pipe line for providing FHTC at Kaluha, Dighuli & Malpara Habitations under Kaluha PWSS under Rampurhat Sub- Division, P.H.E. Dte. | AE | JE2 | ORD/000391/2021-2022 | 372/RSD | 28/09/2021 | 28/10/2021 | PULAK KUMAR PAL | 3.4 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS | SM/06738 | Retrofitting | Additional Laying of UPVC Pipe line for providing FHTC at Jagadishpur & Marbasahar village under Kaluha PWSS within Birbhum Division, P.H.E. Dte. (Sl. No.3) | AE | JE2 | ORD/000848/2021-2022 | 2005/BHM | 08/12/2021 | 06/02/2022 | SANJUKTA ENGINEERS | 6.82 | 0 | 0 | 50
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS | SM/06738 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kaluha, Malpara of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.6) | AE | JE2 | ORD/000048/2020-2021 | 1240/BHM | 28/09/2020 | 27/11/2020 | PULAK KUMAR PAL | 38.12 | 34.9 | 91.56 | 0
Total | [13 empty] | 124.59 | 79.89 | 64.12