## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Hazarpur PWSS(Phase-I) | SM/06739 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hazarpur of Hazarpur w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-A) | AE | JE3 | ORD/000055/2020-2021 | 1180 /BHM | 21/09/2020 | 20/11/2020 | UJJWAL DAS | 41.06 | 84.25 | 205.22 | 0
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Hazarpur PWSS(Phase-I) | SM/06739 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kanakpur, Bholadanga, Ekdala of Hazarpur w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000056/2020-2021 | 1181 /BHM | 21/09/2020 | 20/11/2020 | APORUPA CONSTRUCTION | 42.76 | 87.33 | 204.23 | 0
Total | [13 empty] | 83.82 | 171.59 | 204.71