## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages BAITARA & KHUJUTIPARA of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No. - 08) | AE | JE2,Bolpur Sub-Division | ORD/000518/2021-2022 | 375/BSD | 05/10/2021 | 04/11/2021 | MANAS KUMAR MONDAL | 4.56 | 0 | 0 | 98
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and Retrofitting of pipe lines From Khujutipara Fishery Market to Petrol pump, Chatimgram on Basapara Nanoor Road for Providing sufficient water to Nanagar Kodda Village from existing distribution system within the command area of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED | AE | JE2,Bolpur Sub-Division | ORD/000325/2022-2023 | 2586/BHM | 22/11/2022 | 22/12/2022 | M/S.CHANDRANATH MUKHERJEE | 23.26 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Supply of one no. Diesel driven Motor Cab/Maxi Cab(Air Condition) on hire basis under the Assistant Engineer (H.Q), Birbhum Division PHE Dte.(Period from 01.11.2022 to 30.04.2023) | AE(HQ) | Estimator | ORD/000531/2022-2023 | 2320/BHM | 28/10/2022 | 30/04/2023 | JAMSED ALI KHAN | 0.96 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Supply of one no. diesel driven Car (Diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS, Birbhum Sub-Division, P.H.E. Dte. [Period from (01.02.2023 to 05.07.2023) | AE |  | ORD/000572/2022-2023 | 185/RWS | 31/01/2023 | 05/07/2023 | AADIL CONSTRUCTION | 0.73 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Payment of Deisel Oil and fuel for the month of July23 to Sept'23 |  |  | BILL/00476/2023-2024 | BP-2023-24-235 | 01/11/2023 | 01/11/2023 | JAYRAM FILLING STATION | 0.72 | 0 | 0 | 0
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Payment for Supply of diesel |  |  | BILL/00270/2023-2024 | BP-2023-24-127 | 25/08/2023 | 25/08/2023 | JAYRAM FILLING STATION | 0.72 | 0 | 0 | 0
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, P.H.E. Dte under Birbhum Division, P.H.E Dte. for the period of 01.04.2023 to 30.09.2023 | AE | JE3 | ORD/000684/2022-2023 | 154/BSD | 30/03/2023 | 29/09/2023 | SK AKRAM HOSSAIN | 0.86 | 0 | 0 | 87
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Continution work for Supply of one no. Diesel driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.05.2023 to 31.10.2023) | AE(HQ) | Estimator | ORD/000166/2023-2024 | 1607/BHM | 27/04/2023 | 28/10/2023 | JAMSED ALI KHAN | 0.96 | 0 | 0 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Continuation Work of Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition for 364 days (from 02.07.2021 to 30.06.2022) for 364 days (from 02.07.2022 to 30.06.2023) for 31 Days (from 01.07.2023 to 31.07.2023). | AE | JE3 | ORD/000168/2023-2024 | 155/RSD | 28/06/2023 | 29/07/2023 | SOUMITA PAL | 0.17 | 0 | 0 | 0
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Supply of one no. diesel driven car(Diesel) on hire basis office uses for the official of the Assistant Engineer, RWS, Birbhum Sub-Division, PHE Dte.(Period from 06.07.2023 to 31.12.2023) | AE | JE | ORD/000340/2023-2024 | 337/RWS | 05/07/2023 | 31/12/2023 | AADIL CONSTRUCTION | 0.85 | 0 | 0 | 15
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Continuation order against "Hiring of 1(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE Dte. under Birbhum Division, PHE Dte. For the period of 01.04.2023 to 30.09.2023". For another 06 (Six) months i.e. from 01.10.2023 to 31.03.2024. | AE | JE3 | ORD/000449/2023-2024 | 436/BSD | 29/09/2023 | 29/03/2024 | SK AKRAM HOSSAIN | 0.86 | 0 | 0 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Khujutipara Mouja (JL No.-127) at different locations from existing distribution system within the command area of Khujutipapara and Adjoining Mouzas W/S Scheme at Nanoor Block under Bolpur Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte | AE | JE2,Bolpur Sub-Division | ORD/000084/2020-2021 | 1088 /BHM | 05/09/2020 | 05/10/2020 | BHAGYADHAR GHOSH | 4.7 | 4.7 | 100 | 0
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Nabasta of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.24) | AE | JE2,Bolpur Sub-Division | ORD/000359/2020-2021 | 31/BHM | 13/01/2021 | 14/03/2021 | MANAS KUMAR MONDAL | 28.93 | 13.59 | 46.96 | 45
14 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Preparation and broadcasting of 10 minutes programme (PHE Manusaher sathe) planned for Awarness generation through (Audio visual Documentation) TV and social media of covering the area of Birbhum Distric under Birbhum Division PHE Dte. (Sl.No.01) |  |  | ORD/000192/2020-2021 | 1570/BHM | 07/12/2020 | 05/02/2021 | TARANGA ONLINE | 0.89 | 0.89 | 100 | 0
15 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Cleaning the Chokage of 150mm. DI pipe line, repairing of UPVC pipe, retrofitting of pipeline for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages of Baitara, Sehela and Nabsata of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, Public Health Engineering Department. | AE | JE2, Birbhum Sadar Sub-Division | ORD/000822/2022-2023 | 309/BSD | 16/08/2022 | 15/09/2022 | BHAGYADHAR GHOSH | 4.42 | 0 | 0 | 100
16 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) | SM/06741 | Retrofitting | Certified that the total quantity of fuel supplied for the vehicle no. WB53B-8630 consumed for official purpose under Assistant Engineer (HQ), Birbhum Division PHE Dte. for the month of Oct'23. |  |  | BILL/00883/2023-2024 | BP-2023-24-407 | 01/03/2024 | 01/03/2024 | JAYRAM FILLING STATION | 0.2 | 0 | 0 | 0
Total | [13 empty] | 73.79 | 19.17 | 25.98