## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) | SM/06742 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Saldanga, Dhalla, Lakshmipur, Daranda & Ramnagar of Daranda w/s Scheme at Illambazar Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No.10) | AE | JE1 | ORD/000609/2020-2021 | 1024/BHM | 04/11/2020 | 19/12/2020 | S.S. BHATTACHARJEE. | 13.82 | 0 | 0 | 35
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) | SM/06742 | Retrofitting | Hiring of SWIFT DIZER (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub - Division under Birbhum Division, PHE Dte. (Period from 01.04.2023 to 30.09.2023) 183-Days. | AE | JE1,JE2 | ORD/000607/2022-2023 | 130/AE/NSD | 31/03/2023 | 30/09/2023 | JOY CHAND MAL | 0.86 | 0 | 0 | 85
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) | SM/06742 | Retrofitting | Replacement of damaged UPVC pipe line due to widening of road from Bubahat More towards Chella along with extension of UPVC pipe line for the habitation of Halsidanga, Chella, etc. of Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000819/2021-2022 | 457/BSD | 13/12/2021 | 12/01/2022 | S.S. BHATTACHARJEE. | 4.34 | 0 | 0 | 50
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) | SM/06742 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Daronda w/s Scheme (Left out House Hold) in Bolpur Sub-Division under Birbhum Division, PHE Dte. (2nd Call).¿ (Sl. No.7) | AE | JE1 | ORD/000426/2021-2022 | 2059/BHM | 10/12/2021 | 08/02/2022 | RAJKUMAR DAS | 38.89 | 0 | 0 | 85
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) | SM/06742 | Retrofitting | Payment for Supply of diesel |  |  | BILL/00270/2023-2024 | BP-2023-24-127 | 25/08/2023 | 25/08/2023 | JAYRAM FILLING STATION | 0.72 | 0 | 0 | 0
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) | SM/06742 | Retrofitting | Preparation of Audio clip single of 5 minute aand telecast the same through FM (Air) for a period of 3 month 4 times in a day under Birbhum Diviison PHE Dte. (Sl.No.02) |  |  | ORD/000187/2020-2021 | 1571/BHM | 07/12/2020 | 05/02/2021 | IMAGIN | 0.89 | 0.89 | 100 | 0
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) | SM/06742 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kamarpara & Chella of Daranda w/s Scheme at Illambazar Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.11) | AE | JE1 | ORD/000078/2020-2021 | 1425/BHM | 04/11/2020 | 19/12/2020 | SYED KHORSID ALAM | 17.6 | 15.61 | 88.72 | 0
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) | SM/06742 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chella, Ramnagar, Bonovilla, Lakshipur, Daronda, Dhalla, Saldanga, Usurdihi, Ushahar etc. in different locations under Daronda Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.1) | AE,Assistant Engineer | JE1 | ORD/000122/2022-2023 | 1569/BHM | 26/07/2022 | 24/09/2022 | HOQUEDAR ALI | 43.32 | 0 | 0 | 100
Total | [13 empty] | 120.44 | 16.5 | 13.7