## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) | SM/06743 | Retrofitting | Providing Tap Connection for Existing School & AWC in Naryanpur PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000079/2021-2022 | 278/RSD | 16/07/2021 | 26/07/2021 | SHIB GANGA CONSTRUCTION | 0.5 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) | SM/06743 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Balia Mrityunjoypur of Narayanpur w/s Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE1 | ORD/000607/2020-2021 | 1706 /BHM | 23/12/2020 | 21/02/2021 | SANJUKTA ENGINEERS | 36.44 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) | SM/06743 | Retrofitting | Additional FHTC works from existing distribution system at Narayanpur mouza within Narayanpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-30) | AE | JE1 | ORD/000179/2022-2023 | 273/RSD | 16/08/2022 | 15/09/2022 | SUNIL RABI DAS | 4.85 | 0 | 0 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) | SM/06743 | Retrofitting | Additional FHTC works from existing distribution system at Narayanpur habitation within Narayanpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-31) | AE | JE1 | ORD/000180/2022-2023 | 277/RSD | 18/08/2022 | 17/09/2022 | SUNIL RABI DAS | 4.89 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) | SM/06743 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Narayanghati w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-2) | AE | JE1 | ORD/000365/2021-2022 | 1915/BHM | 24/11/2021 | 23/01/2022 | TAPAN KUMAR DATTA | 82.11 | 0 | 0 | 53
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) | SM/06743 | Retrofitting | Sinking of o1 (one) No 200mm dia.X 42.0 mtr deep Tube Well with UPVC pipe & strainer for Narayanpur W/s scheme under Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000543/2021-2022 | 30/RSD | 04/01/2022 | 03/02/2022 | ISLAM CONSTRUCTION | 2.92 | 0 | 0 | 50
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) | SM/06743 | Retrofitting | Laying Bypass UPVC Pipe line from CWR to Suripara more for providing drinking water Hattala surrounding Area of Narayanpur W/S Scheme under Rampurhat Sub-Division, P.H.E. Dte within Birbhum Division, P.H.E. Dte. (Sl. No.2) | AE | JE1 | ORD/000815/2021-2022 | 2069/BHM | 13/12/2021 | 11/02/2022 | ISLAM CONSTRUCTION | 13.26 | 0 | 0 | 50
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) | SM/06743 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Balia Mrityunjoypur of Narayanpur w/s Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE1 | ORD/000226/2020-2021 | 1706/BHM | 23/12/2020 | 21/02/2021 | SANJUKTA ENGINEERS | 36.44 | 25.01 | 68.63 | 27
Total | [13 empty] | 181.41 | 25.01 | 13.79