## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Bhabanandapur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000286/2021-2022 | 510/AE/NSD | 01/10/2021 | 15/11/2021 | SURJASISH DATTA | 4.67 | 0 | 0 | 50
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasipur Dakshinpara and its adjoining areas, under Nasipur Habitation within Bhabanandapur village (J.L.-24) under Nalhati-1 Block within the command area of Bhabanandapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000436/2020-2021 | 53/AE/NSD | 08/02/2021 | 09/04/2021 | MD SHAHAJAMAL | 4.98 | 4.98 | 100 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhabanandapur Paschimpara and it's adjoining areas, under Bhabanandapur Habitation under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000454/2020-2021 | 50/AE/NSD | 08/02/2021 | 09/04/2021 | SURJASISH DATTA | 4.59 | 9.18 | 200 | 50
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Jerapara, Nachpahari,Sialdanga, Tarapur Hbitations and it's adjoining areas, under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000504/2020-2021 | 51/AE/NSD | 08/02/2021 | 09/04/2021 | KAZI ZAKIR HOSSAIN | 4.97 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasihapur uttarpara and adjoining areas under Nasihapur Habitation, within Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000505/2020-2021 | 52/AE/NSD | 08/02/2021 | 09/04/2021 | NUR MOBINUL ISLAM | 4.98 | 0 | 0 | 0
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhabanandapur Paschimpara and it's adjoining areas, under Bhabanandapur Habitation under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000503/2020-2021 | 50/AE/NSD | 08/02/2021 | 09/04/2021 | SURJASISH DATTA | 4.59 | 0 | 0 | 50
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasipur Uttarpara and its and adjoining areas under Nasipur Habitaiton within Bhabanandapur villages (JL no 24)under Nalhati I Block within the command area of Bhabandaapur water supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (SL no. 03) | AE | JE1 | ORD/000360/2020-2021 | 52/NSD | 08/02/2021 | 09/04/2021 | NUR MOBINUL ISLAM | 4.98 | 9.96 | 200 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasihapur Purba para and it's adjoining areas, under Nasihapur Habitation under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000506/2020-2021 | 54/AE/NSD | 08/02/2021 | 09/04/2021 | GOLAM RASUL | 4.98 | 9.96 | 200 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Bhabanandapur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000296/2021-2022 | 510/AE/NSD | 01/10/2021 | 15/11/2021 | SURJASISH DATTA | 4.67 | 4.67 | 100 | 50
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Supply of one No. Diesel driven Motor Cab/Maxi Car (Air Condition) on hire basis under the Executive Engineer, Birbhum Division, P.H.E Dte. (Period from 01.11.2022 to 30.04.2023) | AE |  | ORD/000694/2022-2023 | 2322/BHM | 28/10/2022 | 30/04/2023 | PREMANANDA ROY BISWAS | 0.96 | 2.38 | 246.52 | 84
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Extention of UPVC pipeline for providing FHTC in different habitation under Bhabanandapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHED. | AE | JE1 | ORD/000036/2022-2023 | 264/AE/NSD | 11/05/2022 | 25/06/2022 | ASGAR SK | 4.84 | 4.81 | 99.34 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Extension of UPVC pipe line for providing FHTC at Bhabanandapur habitation under Bhabanandapur PWSS under Nalhati Sub-Division, within Birbhum Division P.H.E Dte. | AE | JE1 | ORD/000054/2022-2023 | 281/NSD | 20/05/2022 | 19/06/2022 | SURJASISH DATTA | 1.45 | 1.42 | 97.85 | 100
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Sinking of replacement the tubewell 200mm dia & 87 m. deep with PVC pipe and fibre glass Strainer at Bhabanandapur (near head work side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE | JE1 | ORD/000003/2022-2023 | 207/AE/NSD | 05/04/2022 | 05/05/2022 | A R ENTERPRISE | 4.79 | 0 | 0 | 100
14 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Extention of pipeline by HDPE pipe at Nasipur habitation for providing FHTC of Bhabanandapur W/S Scheme, under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. | AE | JE1 | ORD/000094/2022-2023 | 279/NSD | 20/05/2022 | 19/06/2022 | MD ASIF ALI | 2.16 | 2.15 | 99.54 | 100
15 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Laying distribution system for proposed augmentation scheme for Bara Zone-II Piped Water Supply Scheme under Nalhati-II Block, under Birbhum Division, PHE Dte.(Sl. No.1) | AE | JE2 | ORD/000211/2022-2023 | 805/BHM | 12/04/2022 | 09/10/2022 | MANASH GHOSH | 397.16 | 1.55 | 0.39 | 100
16 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Continuation Work Order for Supply of one no. diesel driven Motor Cab (Non Air-conditioned) on hire basis for official uses of the Assistant Engineer, Birbhum Sadar Sub-Division, P.H.E Dte. (Period from 01.09.2021 to 28.02.2022) | AE | JE | ORD/001171/2021-2022 | 305/BSSD | 31/05/2021 | 30/11/2021 | RITA RABIDAS | 0.71 | 2.36 | 331.45 | 60
17 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Hiring of SWIFT DIZER (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub - Division under Birbhum Division, PHE Dte. (Period from 01.10.2023 to 31.03.2024) 182-Days. | AE | JE1,JE2 | ORD/000375/2023-2024 | 353/NSD | 29/09/2023 | 29/03/2024 | JOY CHAND MAL | 0.86 | 2.28 | 266.52 | 100
18 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Continuation Work of Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Egineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition for 364 days (from 02.07.2021 to 30.06.2022) for 364 days (from 02.07.2022 to 30.06.2023). | AE | JE3 | ORD/000066/2022-2023 | 223/RSD | 23/06/2022 | 22/06/2023 | SOUMITA PAL | 2.04 | 3.94 | 193.27 | 50
19 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Jerapara, Nachpahari, Sialdanga & Tarapur habitation & its adj. areas under Bhabanandapur Village (JL No.24) under Nalhati-I Block, within the command area of Bhabanandapur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.03) | AE | JE1 | ORD/000306/2020-2021 | 51/NSD | 08/02/2021 | 10/03/2021 | KAZI ZAKIR HOSSAIN | 4.97 | 9.95 | 200 | 0
20 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing functional house hold tap connection (FHTC) form existing distribution system in Bhabanandapur Dakshinpara and its adjoining areas of Bhabanandapur Habitation under Bhabanandapur Mouza (J.L.24) under Nalhati-I Block within the command area of Bhabanandapur WS Scheme.(Sl.No.02) | AE | JE1 | ORD/000217/2020-2021 | 1649/BHM | 18/12/2020 | 18/03/2021 | ASGAR SK | 4.7 | 9.4 | 200 | 0
21 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in Bhabanandapur purbapara and its adjoining areas of Bhabanandapur Habitation under Bhabanandapur Mouzas (Jl.24) under Nalhati -I of Bhabanandapur Wsater Supply scheme (Sl.no.03) | AE | JE1 | ORD/000213/2020-2021 | 1650/BHM | 18/12/2020 | 17/04/2021 | SURJASISH DATTA | 4.67 | 9.33 | 200 | 0
22 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in Bhabanandapur Uttarpara and Its adjoining areas of Bhabanandapur Habitation under Bhabanandapur Mouza (JL.24) under Nalhati -I Block. of Bhabanandapur Water Supply Scheme (Sl.No.01) | AE | JE1 | ORD/000204/2020-2021 | 1648/BHM | 18/12/2020 | 18/03/2021 | A R ENTERPRISE | 4.74 | 9.49 | 200 | 0
23 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS | SM/06744 | Retrofitting | Extention of Pipeline along with FHTC at left out habitations of BHABANANDAPUR PWSS under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No.11) | AE | JE1 | ORD/000490/2022-2023 | 289/BHM | 01/02/2023 | 14/09/2023 | M/S SARADA CONSTRUCTION. | 16.48 | 9.46 | 57.36 | 100
Total | [13 empty] | 493.93 | 107.25 | 21.71