## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area | SM/06943 | Retrofitting | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Rajnagar Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 10) | AE | JE | ORD/000405/2021-2022 | 382/BSSD | 10/12/2021 | 30/12/2021 | SUBHANKAR ROY | 0.99 | 0 | 0 | 49
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area | SM/06943 | Retrofitting | Additional work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages of Madarpur, Joypur, Talpukur, Ruhida, Ranigram, Hirapur, Mursabani, Lauberia of Aligarh Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.¿ (Sl. No.2) | AE |  | ORD/000261/2022-2023 | 2152/BHM | 28/09/2022 | 27/11/2022 | M/S KRIPASINDHU GHOSH & CO. | 13.95 | 13.78 | 98.79 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area | SM/06943 | Retrofitting | Additional work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villagesTilabani, Ramnagar, Dhaka, Gangapur, Aligarh of Aligarh Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000269/2022-2023 | 2177/BHM | 29/09/2022 | 28/11/2022 | M/S GOUTAM DAS | 12.16 | 11.58 | 95.22 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area | SM/06943 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Tilabani, Ramnagar, Dhaka, Gangapur, Aligarh of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte | AE | JE3 | ORD/000068/2020-2021 | 1168 /BHM | 21/09/2020 | 20/11/2020 | M/S GOUTAM DAS | 37.14 | 66.24 | 178.32 | 0
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area | SM/06943 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages (Murgathali, Ashna, Sundarkhela, Jahanbal) of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000066/2020-2021 | 1169/BHM | 21/09/2020 | 20/11/2020 | PRANAB KUMAR GHOSH | 40.55 | 57.44 | 141.66 | 0
Total | [13 empty] | 104.8 | 149.04 | 142.21