## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Saldanga, Dhalla, Lakshmipur, Daranda & Ramnagar of Daranda w/s Scheme at Illambazar Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No.10) | AE | JE1 | ORD/000609/2020-2021 | 1024/BHM | 04/11/2020 | 19/12/2020 | S.S. BHATTACHARJEE. | 13.82 | 5.45 | 39.42 | 35
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | Retrofitting | Providing Household Tap Connection (FHTC) at Daronda Mouja ( J.L No 129) at different Location from existing distribution system within the command area of Daronda and adjoining Mouza W/S Scheme at Illambazar Block under Bolpur Sub-Division P.H.E Dte within Birbhum Division P.H.E Dte. | AE | JE1 | ORD/000083/2020-2021 | 1087/BHM | 05/09/2020 | 05/10/2020 | S.S. BHATTACHARJEE. | 4.71 | 9.38 | 199.33 | 0
3 | BIRBHUM |  | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000348/2021-2022 | 402/BSD | 25/10/2021 | 04/11/2021 | NAZIR HOSSAIN | 0.96 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000411/2021-2022 | 402/ BSD | 25/10/2021 | 04/11/2021 | NAZIR HOSSAIN | 0.96 | 0.66 | 68.85 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | Retrofitting | Replacement of UPVC pipe line damaged due to widening of road from Bubahat More towards Chella road along with extension of UPVC pipe line for habitation of Daranda Palpara, Chasapara, Malpara, Bauripara, Darjipara, Suripara, High School Para etc. for Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. 01) | AE | JE1 | ORD/000619/2021-2022 | 241/BSD | 16/07/2021 | 15/08/2021 | S.S. BHATTACHARJEE. | 4.99 | 4.98 | 99.77 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | Retrofitting | Replacement of damaged UPVC pipe line due to widening of road from Bubahat More towards Chella along with extension of UPVC pipe line for the habitation of Halsidanga, Chella, etc. of Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000819/2021-2022 | 457/BSD | 13/12/2021 | 12/01/2022 | S.S. BHATTACHARJEE. | 4.34 | 4.34 | 99.98 | 50
7 | BIRBHUM |  | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Illambazar (Illambazar & Daronda) within Ruppur & Illambazar G.P.under Bolpur Sub-Division within Birbhum Division, PHED | AE | JE1 | ORD/000459/2021-2022 | 16/BSD | 11/01/2022 | 26/01/2022 | GANAPATI ENGINEERING CORP. | 1.97 | 0 | 0 | 48
8 | BIRBHUM |  | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chella, Ramnagar, Bonovilla, Lakshipur, Daronda, Dhalla, Saldanga, Usurdihi, Ushahar etc. in different locations under Daronda Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.1) | AE,Assistant Engineer | JE1 | ORD/000122/2022-2023 | 1569/BHM | 26/07/2022 | 24/09/2022 | HOQUEDAR ALI | 43.32 | 30.63 | 70.72 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | Retrofitting | Hiring of SWIFT DIZER (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub - Division under Birbhum Division, PHE Dte. (Period from 01.04.2023 to 30.09.2023) 183-Days. | AE | JE1,JE2 | ORD/000607/2022-2023 | 130/AE/NSD | 31/03/2023 | 30/09/2023 | JOY CHAND MAL | 0.86 | 1.15 | 133.44 | 85
10 | BIRBHUM |  | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area | SM/06944 | Retrofitting | Continution work for Supply of one no. Diesel Motor Cab/Maxi Cub (Air Condition) on hire basis under the Executive Engineer Birbhum Division P.H.E Dte (Period From 01.05.2023 to 31.10.2023) | AE(HQ) |  | ORD/000165/2023-2024 | 1618/BHM | 27/04/2023 | 27/10/2023 | PREMANANDA ROY BISWAS | 0.96 | 2.37 | 245.72 | 60
Total | [13 empty] | 76.9 | 58.96 | 76.68