## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area | SM/06945 | Retrofitting | Providing Tap Connection for Existing School & AWC under Shilogram, Kamra,Kayemba,Chandpara, Harirampur Mouzas in Dunigram PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000076/2021-2022 | 275/RSD | 16/07/2021 | 26/07/2021 | MD ABSAR ALI | 0.99 | 0 | 0 | 50
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area | SM/06945 | Retrofitting | Laying & distribution system with UPVC pipes including FHTC (Functional Household Tap Connection) for Belera PWSS under Birbhum, Division, PHE Dte | AE | JE3 | ORD/000396/2022-2023 | 2165./BHM | 28/09/2022 | 28/10/2022 | OM ENTERPRISE | 34.22 | 0 | 0 | 30
3 | BIRBHUM |  | Birbhum Division | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area | SM/06945 | Retrofitting | Supply of one no. diesel driven car(Diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS, Birbhum Sub-Division, PHE Dte. (Period from 01.01.2024 to 27.06.2024) | AE | JE | ORD/000616/2023-2024 | 481/RWS | 28/12/2023 | 24/06/2024 | AADIL CONSTRUCTION | 0.85 | 0 | 0 | 52
4 | BIRBHUM |  | Birbhum Division | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area | SM/06945 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Dunigram of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000050/2020-2021 | 1176 /BHM | 21/09/2020 | 20/11/2020 | QUAZI SIRAJUL ISLAM. | 38.07 | 35.58 | 93.47 | 0
5 | BIRBHUM |  | Birbhum Division | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area | SM/06945 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Chandanpara) of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte | AE | JE3 | ORD/000052/2020-2021 | 1175 /BHM | 21/09/2020 | 20/11/2020 | MD ABSAR ALI | 34.27 | 31.42 | 91.69 | 0
Total | [13 empty] | 108.41 | 67.01 | 61.81