## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Hazarpur (Phase-II) water supply scheme under Rampurhat-II Block PWSS for providing Functional Household Tap Connection(FHTC) within command area | SM/06946 | Retrofitting | Laying of Distribution System with UPVC Pipes and Providing Tap Connection for Existing School & AWC under Hazarpur PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000077/2021-2022 | 276/RSD | 16/07/2021 | 26/07/2021 | ABUL HASNAT | 1 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Hazarpur (Phase-II) water supply scheme under Rampurhat-II Block PWSS for providing Functional Household Tap Connection(FHTC) within command area | SM/06946 | Retrofitting | Additional laying of UPVC Pipe line at Hazarpur, Kanakpur & Ekdala Mouzas along with other allied works for providing FHTC under Hazarpur Piped W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte within Birbhum Division P.H.E. Dte. | AE | JE1 | ORD/000392/2021-2022 | 373/RSD | 28/09/2021 | 28/10/2021 | UJJWAL DAS | 2.79 | 2.76 | 99.18 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works of Hazarpur (Phase-II) water supply scheme under Rampurhat-II Block PWSS for providing Functional Household Tap Connection(FHTC) within command area | SM/06946 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Uttarpur, Shinpur, Pariharpur, Jashahari of Hazarpur w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.8) | AE | JE1 | ORD/000049/2020-2021 | 1242 /BHM | 28/09/2020 | 27/11/2020 | NANDANIK ENGINEERS C. OP. SOC. LTD. | 36.52 | 71.48 | 195.72 | 0
Total | [13 empty] | 40.3 | 74.24 | 184.21