## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Chhatingram of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.6) | AE | JE2,Bolpur Sub-Division | ORD/000075/2020-2021 | 1422/BHM | 04/11/2020 | 19/12/2020 | INDRAJIT DAS | 15.08 | 22.36 | 148.34 | 0
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Khujutipara of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.07) | AE | JE2,Bolpur Sub-Division | ORD/000044/2020-2021 | 1460/BHM | 12/11/2020 | 27/12/2020 | MS BUILDWELL | 21.21 | 37.75 | 177.95 | 0
3 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sakadda of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.05) | AE | JE2,Bolpur Sub-Division | ORD/000046/2020-2021 | 1459/BHM | 12/11/2020 | 11/01/2021 | MS B N ENTERPRISES | 27.38 | 40.14 | 146.58 | 0
4 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at different School and Anganwadi Centre in Labpur Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE2,Bolpur Sub-Division | ORD/000501/2021-2022 | 335/ BSD | 06/09/2021 | 21/09/2021 | NAZIR HOSSAIN | 0.1 | 0 | 0 | 50
5 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Nabasta of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.24) | AE | JE2,Bolpur Sub-Division | ORD/000359/2020-2021 | 31/BHM | 13/01/2021 | 14/03/2021 | MANAS KUMAR MONDAL | 28.93 | 0 | 0 | 45
6 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages KHUJUTIPARA of Khujutipara W/S Scheme at Nanoor Block under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE2,Bolpur Sub-Division | ORD/000477/2021-2022 | 373/ BSD | 05/10/2021 | 04/11/2021 | M/S BUILDWELL | 3.82 | 3.81 | 99.81 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sakadda (in the habitation SERPUR AND SAKADDA) of Khujutipara W/S Scheme at Nanoor Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE2,Bolpur Sub-Division | ORD/000417/2021-2022 | 306/BSD | 19/08/2021 | 18/09/2021 | MS B N ENTERPRISES | 4.9 | 7.07 | 144.35 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at different School and Anganwadi Centre in Nanoor Block, Bolpur-Sriniketan Block (Part) under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE2,Bolpur Sub-Division | ORD/000499/2021-2022 | 312/ BSD | 25/08/2021 | 09/09/2021 | NAZIR HOSSAIN | 0.1 | 0.1 | 100 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Survey for Functional Household Tap (FHTC) at different School and Anganwadi Centre in Labpur Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE2,Bolpur Sub-Division | ORD/000500/2021-2022 | 335/ BSD | 06/09/2021 | 21/09/2021 | NAZIR HOSSAIN | 0.1 | 0.1 | 98.7 | 50
10 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Retrofitting of pipe lines From OHR to Khujutipara Fishary Market, Khujutipara for Providing suficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages SAKKADA of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Part -A). | AE | JE2,Bolpur Sub-Division | ORD/000475/2021-2022 | 426/BSD | 22/11/2021 | 22/12/2021 | MANAS KUMAR MONDAL | 4.85 | 4.85 | 99.94 | 100
11 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Retrofitting of pipe lines from Khujutipara Fishary Market to Smashan Kali Mandir, Khujutipar on Basapara-Nanoor Road for Providing Functional Household Tap Connection (FHTC) from existing distribution system at the village Sakadda within the command area of Khujutipara Water Supply Scheme (Part -B) of Bolpur Sub-Division under Birbhum Division, PHED. (Sl. - 08) | AE | JE2,Bolpur Sub-Division | ORD/000523/2021-2022 | 452/BSD | 13/12/2021 | 12/01/2022 | MANAS KUMAR MONDAL | 3.96 | 3.96 | 100 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Nabasta (in the habitation NABASTA) Khujutipara W/S Scheme at Nanoor Block within Bolpur Sub-Division under Birbhum Division P.H.E. Dte. (Mouja: Nabastha Node point 01 to 02) | AE | JE2,Bolpur Sub-Division | ORD/000350/2021-2022 | 327/BSD | 01/09/2021 | 01/10/2021 | MANAS KUMAR MONDAL | 4.84 | 9.22 | 190.35 | 0
13 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Allied works of extension of pipeline for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages of Baitara (in the habitation Suchpur and Baitara Balance) of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Part-II) | Assistant Engineer | JE2 | ORD/001215/2021-2022 | 325/BSD | 01/09/2021 | 16/09/2021 | M/S KRIPASINDHU GHOSH & CO. | 1.2 | 1.07 | 88.62 | 100
14 | BIRBHUM |  | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area | SM/06947 | Retrofitting | Allied works of extension of pipe line for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages of Baitara (in the habitation Suchpur & Baitara) of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. | AE,Assistant Engineer | JE2 ,JE4 | ORD/000333/2021-2022 | 376/BSD | 05/10/2021 | 04/11/2021 | M/S KRIPASINDHU GHOSH & CO. | 4.85 | 3.22 | 66.48 | 100
Total | [13 empty] | 121.31 | 133.64 | 110.16