## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | Retrofitting | Work order for collection of Household Data through Mobile App/Hard copy including Geo-reference and submission of the same in soft copy against completed FHTC works at the command area of Murarai W/S Scheme under Birbhum Division | AE | JE1 | ORD/000254/2021-2022 | 145/BH | 07/09/2021 | 17/09/2021 | M/S S.N CONSTRUCTION | 0.1 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000284/2021-2022 | 508/AE/NSD | 01/10/2021 | 15/11/2021 | SHIB GANGA CONSTRUCTION | 4.67 | 0 | 0 | 67
3 | BIRBHUM |  | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Gopalpur in Gopalpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.15) | AE | JE2 | ORD/000135/2020-2021 | 1710/BHM | 23/12/2020 | 21/02/2021 | SUNIL RABI DAS | 29.13 | 58.25 | 199.98 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Ramchandrapur, Kestara in Gopalpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.14) | AE | JE2 | ORD/000224/2020-2021 | 1712/BHM | 23/12/2020 | 21/02/2021 | MLG CONSTRUCTION | 37.12 | 74.96 | 201.93 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Ramchandrapur and Kestora under Murarai-I Block within the command area of Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000295/2021-2022 | 509/AE/NSD | 01/10/2021 | 15/11/2021 | SUPRABHAT RABIDAS | 4.66 | 0 | 0 | 33
6 | BIRBHUM |  | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Ramchandrapur in Gopalpur w/s Scheme at under Nalhat Sub Division, PHE Dte. (Sl. No.13) | AE | JE2 | ORD/000117/2020-2021 | 1711/BHM | 23/12/2020 | 21/02/2021 | UMWELT ENGINEER PVT. LTD | 31.5 | 62.59 | 198.71 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. | AE | JE2 | ORD/000016/2022-2023 | 229/AE/NSD | 21/04/2022 | 05/06/2022 | MD ZIAUL ISLAM | 3.34 | 0 | 0 | 0
8 | BIRBHUM |  | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000294/2021-2022 | 508/AE/NSD | 01/10/2021 | 15/11/2021 | SHIB GANGA CONSTRUCTION | 4.67 | 0 | 0 | 67
9 | BIRBHUM |  | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Ramchandrapur and Kestora under Murarai-I Block within the command area of Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000285/2021-2022 | 509/AE/NSD | 01/10/2021 | 15/11/2021 | SUPRABHAT RABIDAS | 4.66 | 0 | 0 | 33
10 | BIRBHUM |  | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area | SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. | AE | JE2 | ORD/000141/2022-2023 | 383/AE/NSD | 10/08/2022 | 24/09/2022 | MD ZIAUL ISLAM | 3.34 | 0 | 0 | 50
Total | [13 empty] | 123.19 | 195.81 | 158.95