## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area | SM/06949 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Beja W/S Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000173/2021-2022 | 1325/BHM | 16/08/2021 | 15/10/2021 | PRADIP KUMAR SHARMA | 38.54 | 82.12 | 213.07 | 92
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area | SM/06949 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for Chuatari,Bandihat and Selhat mouzas under Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000528/2021-2022 | 16/RSD | 04/01/2022 | 03/02/2022 | PRADIP KUMAR SHARMA | 4.15 | 4.14 | 99.82 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area | SM/06949 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for Chuatari and Kumarpur Mouzas under Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000529/2021-2022 | 17/RSD | 04/01/2022 | 03/02/2022 | PRADIP KUMAR SHARMA | 4.06 | 4.05 | 99.8 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area | SM/06949 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at Dheka and Hapina Mouzas under Beja Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000521/2021-2022 | 15/RSD | 04/01/2022 | 03/02/2022 | PRADIP KUMAR SHARMA | 4.27 | 4.26 | 99.77 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area | SM/06949 | Retrofitting | Construction of Temporary road including removing of bushes & vegetation for Beja W/S Scheme under Rampurhat Sub-Division, P.H.E. Dte. | AE | JE2 | ORD/000028/2022-2023 | 177/RSD | 29/04/2022 | 29/05/2022 | NEEL ENTERPRISE | 1.84 | 0 | 0 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area | SM/06949 | Retrofitting | Additional laying of distribution system at Beja and Chuatari Mouzas for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. (Sl.No.04) | AE | JE3 | ORD/000169/2022-2023 | 307/RSD | 08/09/2022 | 08/10/2022 | GOURANGA MONDAL | 4.77 | 2.48 | 51.97 | 100
Total | [13 empty] | 57.62 | 97.05 | 168.43