## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Harisara under Nalhati - I Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | SM/06951 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Harisara w/s Scheme in Nalhati Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-6) | AE | JE1 | ORD/000241/2021-2022 | 1334/BHM | 18/08/2021 | 17/10/2021 | PRAVAT SARKAR | 55.76 | 53.11 | 95.25 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Harisara under Nalhati - I Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | SM/06951 | Retrofitting | Extention of UPVC pipe line to the Harisara habitation within Harisara PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000656/2021-2022 | 524/AE/NSD | 08/10/2021 | 07/11/2021 | B.M.SARKAR | 4.82 | 0 | 0 | 0
Total | [13 empty] | 60.58 | 53.11 | 87.67