## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Kalhua(Phase-II) Water Supply Scheme under Rampurhat-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07152 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Uttar Narayanpur, Kurula Ambha of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-A) | AE | JE2 | ORD/000051/2020-2021 | 1178 /BHM | 21/09/2020 | 20/11/2020 | SUNIL RABI DAS | 41.99 | 18.58 | 44.25 | 79
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Kalhua(Phase-II) Water Supply Scheme under Rampurhat-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07152 | Retrofitting | Additional Laying of UPVC Pipe line for providing FHTC at Jagadishpur & Marbasahar village under Kaluha PWSS within Birbhum Division, P.H.E. Dte. (Sl. No.3) | AE | JE2 | ORD/000848/2021-2022 | 2005/BHM | 08/12/2021 | 06/02/2022 | SANJUKTA ENGINEERS | 6.82 | 6.71 | 98.27 | 50
3 | BIRBHUM |  | Birbhum Division | Retrofitting works of Kalhua(Phase-II) Water Supply Scheme under Rampurhat-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07152 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Mara Basahar, Jagadispur of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-B) | AE | JE2 | ORD/000054/2020-2021 | 1179 /BHM | 21/09/2020 | 20/11/2020 | SANJUKTA ENGINEERS | 32.72 | 56.01 | 171.22 | 100
Total | [13 empty] | 81.53 | 81.3 | 99.72