## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Balia Mrityunjoypur of Narayanpur w/s Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE1 | ORD/000226/2020-2021 | 1706/BHM | 23/12/2020 | 21/02/2021 | SANJUKTA ENGINEERS | 36.44 | 0 | 0 | 27
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | Retrofitting | Laying of Distribution System by HDPE pipe below heavy duty PWD concrete Road at Narayanpur for Narayanpur Water Supply Scheme Form Bhawani Padmabati Pry School to Narayanpur High School under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. (Sl. No.4) | AE | JE1 | ORD/000842/2021-2022 | 622/BHM | 11/03/2022 | 10/05/2022 | SANJUKTA ENGINEERS | 6.96 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | Retrofitting | Sinking of o1 (one) No 200mm dia.X 42.0 mtr deep Tube Well with UPVC pipe & strainer for Narayanpur W/s scheme under Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000543/2021-2022 | 30/RSD | 04/01/2022 | 03/02/2022 | ISLAM CONSTRUCTION | 2.92 | 0 | 0 | 50
4 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | Retrofitting | Laying Bypass UPVC Pipe line from CWR to Suripara more for providing drinking water Hattala surrounding Area of Narayanpur W/S Scheme under Rampurhat Sub-Division, P.H.E. Dte within Birbhum Division, P.H.E. Dte. (Sl. No.2) | AE | JE1 | ORD/000815/2021-2022 | 2069/BHM | 13/12/2021 | 11/02/2022 | ISLAM CONSTRUCTION | 13.26 | 0 | 0 | 50
5 | BIRBHUM |  | Central Drilling | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR NARAYANPUR W/S SCHEME, SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000279/2022-2023 | 1132/CDD | 04/11/2022 | 04/12/2022 | MENAKA ENTERPRISE | 11.09 | 0 | 0 | 92
6 | BIRBHUM |  | Central Drilling | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR NARAYANPUR W/S SCH, SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. |  |  | ORD/000278/2022-2023 | 1133/CDD | 04/11/2022 | 04/12/2022 | MENAKA ENTERPRISE | 8.09 | 0 | 0 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | Retrofitting | Payment for Supply of diesel |  |  | BILL/00270/2023-2024 | BP-2023-24-127 | 25/08/2023 | 25/08/2023 | JAYRAM FILLING STATION | 0.72 | 0 | 0 | 0
8 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Narayanpur of Narayanpur w/s Scheme at Rampurhat-I Block under Birbhum Division, PHE Dte. (Sl. No.12) | AE | JE1 | ORD/000042/2020-2021 | 1426 / BHM | 04/11/2020 | 03/01/2021 | SUNIL RABI DAS | 35.91 | 35.58 | 99.07 | 0
9 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07153 | Retrofitting | PCC Work for road restoration at Hattala due to laying of 160mm dia HDPE Bypass Pipe line from CWR to Suripara more for providing drinking water at Hattala surrounding Area of Narayanpur W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte within Birbhum Division P.H.E. Dte | AE | JE3 | ORD/000585/2022-2023 | 1012/BHM | 30/03/2023 | 14/05/2023 | ISLAM CONSTRUCTION | 4.17 | 0 | 0 | 0
Total | [13 empty] | 119.57 | 35.58 | 29.75