## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07154 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kot w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-4) | AE | JE1 | ORD/000851/2021-2022 | 1323/ BHM | 16/08/2021 | 15/10/2021 | M/S GOUTAM DAS | 93.02 | 26.85 | 28.86 | 65
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07154 | Retrofitting | Supply and delivery of Sluice Valve & Duck Foot Bend for Kot W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.? (Sl. No.4) | AE | JE1 | ORD/000865/2021-2022 | 377/BHM | 21/02/2022 | 08/03/2022 | SSPR VALVE MANUFACTURING PVT LTD | 6.99 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07154 | Retrofitting | Allied works for Providing FHTC from existing distribution system under Kot Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000105/2023-2024 | 2059/BHM | 08/06/2023 | 23/07/2023 | SAPTADIP CONSTRUCTION | 54.29 | 18.19 | 33.5 | 35
4 | BIRBHUM |  | Birbhum Division | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07154 | Retrofitting | Construction of CWR Capacity 45000 cit under Tilpara W/S Scheme under Birbhum Sadar Sub Divn PHE Dte. |  |  | ORD/2011-2012/000162 | 1018/BHM | 17/10/2011 |  | M/S GOUTAM DAS | 3.59 | 38.68 | 1077.03 | 0
Total | [13 empty] | 157.89 | 83.72 | 53.02