## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07155 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hatina, Uchpur, Narayanpur, Gopinathpur ,Basudebpur in Basudebpur w/s Scheme under Rampurhat Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.2) | AE | JE3 | ORD/000159/2021-2022 | 1286/BHM | 10/08/2021 | 09/10/2021 | BANERJEE CONSTRUCTION | 36.47 | 35.5 | 97.35 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07155 | Retrofitting | Allied works for Providing FHTC from existing distributin system at Hatina mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. | AE | JE2 | ORD/000579/2021-2022 | 05/RSD | 04/01/2022 | 03/02/2022 | M/S BUILDWELL | 4.99 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07155 | Retrofitting | Allied works for Providing FHTC from existing distributin system at Narayanpur mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte | AE | JE2 | ORD/000508/2021-2022 | 06/RSD | 04/01/2022 | 03/02/2022 | M/S BUILDWELL | 4.99 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07155 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at mouza Chotto Bataspur, Gopinathpur & Uchpur within Basudebpur PWSS under Rampurhat Sub-Division, P.H.E. Dte. | AE | JE2 | ORD/000506/2021-2022 | 03/RSD | 04/01/2022 | 03/02/2022 | SOIL STORY | 4.95 | 4.95 | 99.89 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07155 | Retrofitting | Allied works for Providing FHTC from existing distributin system at Hatina mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. | AE | JE2 | ORD/000592/2020-2021 | 05/RSD | 04/01/2021 | 03/02/2021 | M/S BUILDWELL | 4.99 | 7.77 | 155.61 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07155 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at Basudebpur mouza under Basudebpur PWSS under Rampurhat Sub- Division, P.H.E. Dte. | AE | JE2 | ORD/000505/2021-2022 | 02/RSD | 04/01/2022 | 03/02/2022 | BANERJEE CONSTRUCTION | 2.62 | 2.61 | 99.67 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07155 | Retrofitting | Providing FHTC from existing distributin system at Gargara mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. | AE | JE2 | ORD/000540/2021-2022 | 27/RSD | 04/01/2022 | 03/02/2022 | JAYANTA BARAL | 4.99 | 4.99 | 99.85 | 80
8 | BIRBHUM |  | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme | SM/07155 | Retrofitting | Providing FHTC from existing distributin system at Pukhur Para mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. | AE | JE3 | ORD/000541/2021-2022 | 28/RSD | 04/01/2022 | 03/02/2022 | ABUL HASNAT | 5 | 4.99 | 99.85 | 100
Total | [13 empty] | 69 | 60.8 | 88.11