## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum | SM/07530 | Retrofitting | Additional work for Construction of 300 Cum Capacity and 20.0m Staging Height RCC Over Head Reservoir & Laying Distribution System including all allied Works as per departmental drawing at Zone-I of Babuijore Piped Water Supply Scheme under Birbhum Sadar Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. (2nd Phase)(Sl. No. - 05) | AE |  | ORD/000622/2021-2022 | 402/BSSD | 14/12/2021 | 29/12/2021 | SUNDAR CONSTRUCTION | 4.63 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum | SM/07530 | Retrofitting | Construction of drain & repairing of Culvert for 300 mm dia. rising main crossing under Culvert at Bara village of Babuijore Piped Water Supply Scheme under Birbhum Sadar Sub-Dvision, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. (Sl. No. - 03) | AE | JE1 | ORD/000864/2021-2022 | 401/BSSD | 14/12/2021 | 29/12/2021 | HIRANMAY GHOSH | 2.03 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum | SM/07530 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Babuijore Zone-II Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte. (2nd Call) (Sl. No.12) | AE | JE2 | ORD/000021/2022-2023 | 819/BHM | 13/04/2022 | 12/06/2022 | PRAVAT SARKAR | 76.14 | 72.78 | 95.58 | 87
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum | SM/07530 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area village of Barrah, Kadamdanga & Dhulkumro of Babuijore (Zone-II) Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No.1) | AE | JE | ORD/000293/2022-2023 | 2433/BHM | 02/11/2022 | 01/01/2023 | PRAVAT SARKAR | 87.09 | 80.36 | 92.27 | 82
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum | SM/07530 | Retrofitting | Laying of distribution system including FHTC for village Geruapahari, J.L No.74, G.P Babuijore, Block Khorasole for ensuing draught like situation within Birbhum Division, PHE Dte.? (Sl. No.5) | AE | JE | ORD/000873/2021-2022 | 507 / BHM | 03/03/2022 | 17/04/2022 | DIPAK SARKAR | 12.24 | 12.22 | 99.86 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum | SM/07530 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Babuijore Zone-I Water Supply Scheme within Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.9) | AE | JE1 | ORD/000463/2021-2022 | 136/BHM | 25/01/2022 | 26/03/2022 | HIRANMAY GHOSH | 76.5 | 76.16 | 99.56 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum | SM/07530 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area village of Barrah, Kadamdanga and Kaithi of Babuijore (Zone-II) Piped Water Supply Scheme under Birbhum Sadar Sub Division , P.H.E Dte within Birbhum Division P.H.E Dte. | AE | JE | ORD/000086/2023-2024 | 1635/BHM | 02/05/2023 | 01/07/2023 | THREE MAA ENTERPRISE | 70 | 44.03 | 62.9 | 100
Total | [13 empty] | 328.62 | 285.55 | 86.89