## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maldanga Zone-I Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte¿(Sl. No.7) | AE | JE3 | ORD/000482/2021-2022 | 278/BHM | 09/02/2022 | 10/04/2022 | APORUPA CONSTRUCTION | 63.41 | 63.34 | 99.9 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maldanga Zone-II Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.8) | AE | JE3 | ORD/000483/2021-2022 | 281/BHM | 09/02/2022 | 10/04/2022 | BIJOY KUMAR CHOUDHURY | 52.83 | 43.55 | 82.44 | 95
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Surveying, Planning etc. including obtaining permission on behalf of PHE Dte Supply, Laying & Pushing of 600 mm dia. 10 mm thick M.S Spiral Welded Casing Pipe by of Fe 410 grade as per IS: 3589-2001 Adopting Trenchless Technologies (Jack Pushing Method) under in between NH road crossing for 200 mm dia. Distribution Line at Joypur More (Node Point 25) under Maldanga W/S Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.1) | AE(HQ) |  | ORD/000715/2021-2022 | 524/BHM | 11/03/2022 | 25/04/2022 | MANASH GHOSH | 19.61 | 0 | 0 | 50
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Supply & delivery of sluice valve for Maldanga Zone-I W/S scheme under Birbhum Division, PHE Dte including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. (Sl. No.-01) | AE(HQ) |  | ORD/000828/2021-2022 | 419/BHM | 24/02/2022 | 11/03/2022 | BIJOY KUMAR CHOUDHURY | 0.92 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for balance Household from existing distribution system within the command area of Maldanga under Maldanga Water Supply Scheme within Birbhum Division, PHE Dte. | AE(HQ) | Estimator | ORD/000092/2022-2023 | 1452/BHM | 07/07/2022 | 05/09/2022 | APORUPA CONSTRUCTION | 64.41 | 50 | 77.63 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum | SM/07532 | Retrofitting | Withdrawing & restroration of 100 mm & 200 mm dia distribution & rising main pipe line at bridge crossing near Maldanga village & providing FHTC for the village of Moulpur, Bhututa & chatrama to declre "SAJAL GRAM" of Maldanga piped water supply scheme under Birbhum division P.H.E Dte. | AE(HQ) | Estimator | ORD/000154/2023-2024 | 1172/BHM | 11/04/2023 | 26/04/2023 | SOURAV MONDAL | 0.98 | 0.97 | 99.34 | 100
Total | [13 empty] | 202.15 | 157.86 | 78.09