## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Providing Tap Connection for Existing School & AWC in Atla PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000074/2021-2022 | 273/RSD | 16/07/2021 | 26/07/2021 | PROLOY KUMAR MONDAL | 0.22 | 0.22 | 99.85 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in Kabichandrapur letpara area under Habitation under Atla Mouzas of Atla Water Ssupply Scheme (Sl.No.03) |  |  | VCH/001028/2020-2021 |  | 17/03/2021 | 17/03/2021 | MD NUREL HOQUE. | 4.02 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Sinking of 02 (Two) No 200mm dia.X 36 mtr deep Tube Well with UPVC pipe & strainer for strengthening of Atla W/S scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl.No-35) | AE | JE3 | ORD/000204/2022-2023 | 338/RSD | 08/09/2022 | 08/10/2022 | SUMAN CHOWDHURY | 3.66 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in kabichandrapur area under kobichandrapur under Atla mouza under Rampurhat -I block at ATLA WS scheme.(Sl.No.01) | AE | JE2 | ORD/000159/2020-2021 | 13/RSD | 11/01/2021 | 10/02/2021 | SUBODH KR MANDAL | 4.98 | 9.97 | 200 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in kabichandrapur area under kobichandrapur under Atla mouza under Rampurhat -I block at ATLA WS scheme.(Sl.No.02) | AE | JE2 | ORD/000160/2020-2021 | 14/RSD | 11/01/2021 | 10/02/2021 | MUKADDUMUL MOULA | 4.59 | 9.02 | 196.75 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Atla W/S Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000172/2021-2022 | 1324/BHM | 16/08/2021 | 15/10/2021 | BIJOY KUMAR CHOUDHURY | 35.94 | 33.87 | 94.25 | 99
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at Kabichandrapur (Adibasipara) at Atla Mouzas under Atla PWSS under Rampurhat SubDivision, within Birbhum Division P.H.E Dte. | AE | JE3 | ORD/000511/2021-2022 | 09/RSD | 04/01/2022 | 03/02/2022 | BIJOY KUMAR CHOUDHURY | 4.98 | 4.97 | 99.69 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Connection with DI pipe from new Tubewell to CWR for Atla PWSS under Rampurhat Sub-Division, P.H.E Dte. | AE | JE2 | ORD/000584/2021-2022 | 68/RSD | 08/02/2022 | 10/03/2022 | PROLOY KUMAR MONDAL | 0.64 | 0 | 0 | 0
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC for Atla Water Supply Scheme at Atla Mouza towards Mollarpur Road, under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. | AE | JE3 | ORD/000513/2021-2022 | 11/RSD | 04/01/2022 | 03/02/2022 | BIJOY KUMAR CHOUDHURY | 2.92 | 2.89 | 98.7 | 100
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Additional Laying of Distribution System for strengthening of Atla Water Supply Scheme for Atla Mouza under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. | AE | JE3 | ORD/000069/2022-2023 | 226/RSD | 23/06/2022 | 23/07/2022 | SUMAN CHOWDHURY | 2.84 | 2.82 | 99.42 | 100
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC for Atla Water Supply Scheme at Atla Mouza Towards Tarapith Roadunder Rampurhat Sub-Division within Birbhum Division P.H.E Dte. | AE | JE3 | ORD/000512/2021-2022 | 10/RSD | 04/01/2022 | 03/02/2022 | BIJOY KUMAR CHOUDHURY | 4.92 | 4.92 | 99.87 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Providing FHTC from existing distributin system in Junidpur, Kamdebpur and Atla mouza within Atla w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. | AE | JE2 | ORD/000380/2021-2022 | 360/RSD | 28/09/2021 | 28/10/2021 | PROLOY KUMAR MONDAL | 2.21 | 1.37 | 61.97 | 0
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Providing Functional Household Tap connection (FHTC) from existing distribution system in Kabichandrapur under Kabichandrapur Habitation under Atla Mouzas under Rampurhat Sub Division PHE Dte. | AE | JE2 | ORD/000189/2020-2021 | 15/RSD | 11/01/2021 | 12/03/2021 | MD NUREL HOQUE. | 4.02 | 8.05 | 200 | 0
14 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Laying of Distribution System for Atla Water Supply Scheme from Mukti Hotel and Residency to Sri Sri Mohananda Brahamchari Sevasharam at Atla Mouzas under Rampurhat Sub-Division, within Birbhum Division P.H.E. Dte. | AE | JE3 | ORD/000118/2021-2022 | 291/RSD | 26/07/2021 | 25/08/2021 | BIJOY KUMAR CHOUDHURY | 4.83 | 0.43 | 8.95 | 0
15 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block | SM/07645 | Retrofitting | Extension of pipe line for providing 04 (four) nos. left out Institutional house connections near Bamakhapa Mandir under Atla PWSS within Rampurhat Sub-Division, P.H.E. Dte. | AE | JE1,JE2 | ORD/000214/2025-2026 | 2184/BHM | 21/08/2025 | 05/10/2025 | MUKADDUMUL MOULA | 1.51 | 0 | 0 | 100
Total | [13 empty] | 82.31 | 78.53 | 95.41