## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in Purba Narayanpur Mouza from existing distribution system within the command area of Nachansaha & Adjoining Mouzas Water Supply Scheme under Bolpur Sub-Division of Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE4 | ORD/000397/2020-2021 | 257/BHM | 26/02/2021 | 12/04/2021 | NAZIR HOSSAIN | 4.66 | 7.59 | 162.77 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in within the command area of village Nachansaha Water Supply Scheme. |  |  | VCH/001029/2020-2021 |  | 17/03/2021 | 17/03/2021 | PINTU KHAN | 4.28 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Providing functional Household tap connection (FHTC) in village Nachansaha (part) from existing distribution system within the command area of Nachansaha & Adjoining mouzas water supply scheme under Bolpur Sub Division PHE (Sl.No.05) |  |  | VCH/001035/2020-2021 |  | 19/03/2021 | 19/03/2021 | SUBHRADIP SARKAR | 4.45 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nachansa w/s Scheme (Leftout House Hold) in Bolpur Sub-Division under Birbhum Division, PHE Dte.(Sl. No.7) | AE | JE4 | ORD/000273/2021-2022 | 1526/BHM | 13/09/2021 | 12/11/2021 | S R ENTERPRISE | 48.52 | 48.02 | 98.97 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Retrofitting of existing distribution Pipeline with Sluice Valve at different Locations of PURBA NARAYANPUR Mouza within the command area of Nachansaha and its Adjoining Mouzas W/S Scheme for providing FHTC under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No. -14) | AE | JE4 | ORD/000554/2021-2022 | 377/ BSD | 05/10/2021 | 04/11/2021 | PINTU KHAN | 4.83 | 4.82 | 99.73 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000348/2021-2022 | 402/BSD | 25/10/2021 | 04/11/2021 | NAZIR HOSSAIN | 0.96 | 0 | 0 | 0
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000411/2021-2022 | 402/ BSD | 25/10/2021 | 04/11/2021 | NAZIR HOSSAIN | 0.96 | 0 | 0 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Retrofitting works to the existing distribution System for providing FHTC within the coverage area of Nachansaha & its Adj. Moujas Water Supply Scheme at Shibpur Mouja and Jagdalpur village (Part) of Bilati G.P. under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 05) | AE | JE4 | ORD/000706/2021-2022 | 449/BSD | 10/12/2021 | 09/01/2022 | S R ENTERPRISE | 4.81 | 4.63 | 96.26 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Retrofitting works to the existing distribution System for FHTC within the coverage area of Nachansaha & Adj. Moujas Water Supply Scheme at GOLTIKURI village (Part) and Nachansaha Mouja (Part) of Bilati G.P. within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 03) | AE | JE4 | ORD/000702/2021-2022 | 424/BSD | 18/11/2021 | 18/12/2021 | S R ENTERPRISE | 4.84 | 4.63 | 95.68 | 100
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Restoration of Cement concrete Road, damaged due to laying of Pipeline during FHTC work at NACHANSAHA and Purba-Narayanpur Moujas at Bilati G.P. within the coverage area of Nachansaha & Adj. Moujas Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 05). | AE | JE4 | ORD/000812/2021-2022 | 102/BSD | 16/03/2022 | 26/03/2022 | S R ENTERPRISE | 0.93 | 0.93 | 99.54 | 100
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in within the command area of village Nachansaha Water Supply Scheme. | AE | JE4 | ORD/000207/2020-2021 | 95/BHM | 29/01/2021 | 29/04/2021 | PINTU KHAN | 4.66 | 9.32 | 200 | 0
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in within the command area of village Nachansaha Water Supply Scheme.(Sl No. 05) | AE |  | ORD/000208/2020-2021 | 256/BHM | 26/02/2021 | 27/05/2021 | SUBHRADIP SARKAR | 4.67 | 8.96 | 192.08 | 0
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block | SM/07646 | Retrofitting | Extension of Pipeline from existing distribution System for providing FHTC at Jagdalpur village of Shibpur Mouza within the coverage area of Nachansaha & Adj. Moujas Water Supply Scheme at Bilati G.P. within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.10) | AE | JE4 | ORD/000434/2021-2022 | 2164/BHM | 24/12/2021 | 22/02/2022 | M/S.CHANDRANATH MUKHERJEE | 18.6 | 2.88 | 15.48 | 100
Total | [13 empty] | 107.19 | 91.79 | 85.63