## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Construction of PCC approach Road at Head Work Site for Raypur Zone-I Piped Water Supply Scheme under under Rampurhat Sub-Division under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000068/2022-2023 | 225/RSD | 23/06/2022 | 23/07/2022 | GOURANGA MONDAL | 2.6 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Supply & delivery of CIDF Sluice Valves for Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I & II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000667/2021-2022 | 119/RSD | 11/03/2022 | 10/04/2022 | ASIT GHOSH | 0.55 | 0 | 0 | 50
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-II Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.13) | AE | JE3 | ORD/000433/2021-2022 | 24/BHM | 06/01/2022 | 07/03/2022 | SK ALIM | 75.03 | 0 | 0 | 97
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-I Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.12) | AE | JE3 | ORD/000480/2021-2022 | 279/BHM | 09/02/2022 | 10/04/2022 | PRADIP KUMAR SHARMA | 76.52 | 0 | 0 | 50
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Additional Laying & joining with UPVC pipes within distribution system From near OHR Site to Deucha Masjid of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000545/2021-2022 | 32/RSD | 04/01/2022 | 03/02/2022 | GOURANGA MONDAL | 4.96 | 0 | 0 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Additional Laying & joining with UPVC pipes within distribution system From near Deucha Bus Stand to Deucha Bridge of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000547/2021-2022 | 34/RSD | 04/01/2022 | 03/02/2022 | GOURANGA MONDAL | 4.95 | 0 | 0 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Supply & delivery of CI/DI Specials for Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I & II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000646/2021-2022 | 117/RSD | 10/03/2022 | 09/04/2022 | ASIT GHOSH | 0.46 | 0 | 0 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Supply & delivery of CIDF Sluice Valves for Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I & II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte | AE | JE3 | ORD/000698/2021-2022 | 119/RSD | 11/03/2022 | 10/04/2022 | ASIT GHOSH | 0.55 | 0 | 0 | 50
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Laying of UPVC pipes within distribution system from Deucha to Harinsingha Road at Sahapara of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000643/2021-2022 | 100/RSD | 07/03/2022 | 06/04/2022 | GOURANGA MONDAL | 2.34 | 0 | 0 | 100
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Laying of HDPE Pipe line for Deucha, Dubrajpur mouzas for providing FHTC under Raypur Zone II Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000030/2022-2023 | 179/RSD | 02/05/2022 | 01/06/2022 | SK ABDUL HALIM | 4.67 | 0 | 0 | 100
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Laying of HDPE Pipe line for Deucha mouza for providing FHTC under Raypur Zone II Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000031/2022-2023 | 180/RSD | 02/05/2022 | 01/06/2022 | SK ABDUL HALIM | 5 | 0 | 0 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Laying of HDPE Pipe line for Uska, Tentulia, Dubrajpur, Raghunathpur mouzas for providing FHTC under Raypur Zone II Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000029/2022-2023 | 178/RSD | 02/05/2022 | 01/06/2022 | SK ABDUL HALIM | 4.99 | 0 | 0 | 100
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Supply & delivery of sluice valve for Raipur W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-02) | AE |  | ORD/000725/2021-2022 | 420/BHM | 24/02/2022 | 11/03/2022 | UJJWAL DAS | 4.59 | 0 | 0 | 100
14 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Additional Laying & joining with UPVC pipes within distribution system From near Deucha Masjid to Deucha Eid Gaha of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000546/2021-2022 | 33/RSD | 04/01/2022 | 03/02/2022 | GOURANGA MONDAL | 4.96 | 0 | 0 | 100
15 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Sinking for 3 nos. 200 mm dia. Tubewell with horizontal strainer on the River Bed of Dwarka under Raypur Piped Water Supply Scheme under Birbhum Division P.H.E. Dte. | AE | JE3 | ORD/000544/2021-2022 | 31/RSD | 04/01/2022 | 03/02/2022 | SUNIL RABI DAS | 4.91 | 0 | 0 | 100
16 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Connection between New Tubewells to existing CWR by DI pipe near Dwarka River Bank site for Raypur Piped Water Supply Scheme under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. | AE | JE3 | ORD/000520/2021-2022 | 14/RSD | 04/01/2022 | 03/02/2022 | ASIT GHOSH | 3.34 | 0 | 0 | 100
17 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block | SM/07649 | Retrofitting | Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I and II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub-Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte. (Sl. No.1) | AE | JE3 | ORD/000861/2021-2022 | 1339/BHM | 18/08/2021 | 27/03/2022 | ASIT GHOSH | 7.34 | 0 | 0 | 100
Total | [13 empty] | 207.75 | 0 | 0