## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | SM/07650 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system for left out Households of the village Hate-Serandi under Hate-Serandi Water Supply Scheme of Bolpur Sub-Division under Birbhum Division, PHED. | AE | JE4 | ORD/000409/2021-2022 | 448/BSD | 10/12/2021 | 09/01/2022 | BISWARUP GHOSH | 4.85 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | SM/07650 | Retrofitting | Retrofitting of pipe lines at Paschimpara, Daspara, Thanderpar and Dakshinpara for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of the village Hate-Serandi under Hate-Serandi Water Supply Scheme of Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE4 | ORD/000410/2021-2022 | 450/BSD | 10/12/2021 | 09/01/2022 | PRATICK KUMAR GHOSH | 4.14 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | SM/07650 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Hateserandi w/s Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-7) | AE | JE2,Bolpur Sub-Division | ORD/000248/2021-2022 | 1462/BHM | 02/09/2021 | 01/11/2021 | BISWARUP GHOSH | 42.56 | 0 | 0 | 98
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | SM/07650 | Retrofitting | Additional pipe line works against laying distribution system of Hate Sarandi Piped Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, P.H.E. Dte |  |  | ORD/000666/2020-2021 | 586 /BHM | 09/06/2020 | 09/07/2020 | GOUTAM DAS | 4.97 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | SM/07650 | Retrofitting | Supply and delivery of 80mm. dia. Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Hateserandi Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 01). | AE | JE2,Bolpur Sub-Division | ORD/000802/2021-2022 | 26/BSD | 21/01/2022 | 05/02/2022 | M/S GOUTAM DAS | 0.65 | 0 | 0 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | SM/07650 | Retrofitting | Retrofitting of parallel pipe lines From Node point 34 to Node point 16 for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages HateSerandi of HateSerandi Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 11). | AE | JE2,Bolpur Sub-Division | ORD/000708/2021-2022 | 53/BSD | 17/02/2022 | 19/03/2022 | BISWARUP GHOSH | 4.43 | 0 | 0 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | SM/07650 | Retrofitting | Construction of Boundary Wall with Drain at west side of HateSerandi OHR site of HateSerandi Scheme under Bolpur Sub-Division within Birbhum Division PHE Dte. (Length 55 Mtr.) (Part -II). (Sl. No.: 10). | AE | JE2,Bolpur Sub-Division | ORD/000821/2021-2022 | 59/BSD | 22/02/2022 | 23/04/2022 | PRATICK KUMAR GHOSH | 4.85 | 0 | 0 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | SM/07650 | Retrofitting | Additional Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hateserandi of Hateserandi Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 01). | AE | JE2,Bolpur Sub-Division | ORD/000048/2022-2023 | 188/BSD | 11/05/2022 | 10/06/2022 | BISWARUP GHOSH | 3.68 | 0 | 0 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block | SM/07650 | Retrofitting | Retrofitting of pipe lines at Habitation Natungram for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hateserandi of Hateserandi Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 05). | AE | JE2,Bolpur Sub-Division | ORD/000049/2022-2023 | 186/BSD | 11/05/2022 | 10/06/2022 | PRATICK KUMAR GHOSH | 4.43 | 0 | 0 | 100
Total | [13 empty] | 74.57 | 0 | 0