## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasa w/s Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.15) | AE | JE1 | ORD/000428/2021-2022 | 2166/BHM | 24/12/2021 | 22/02/2022 | RICK CONSTRUCTION | 48.67 | 0 | 0 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Dompara & Colony under Rasa Mouza (J.L. No.107) under Khoyrasole Block within the command area of RASA Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.28) | AE |  | ORD/000020/2021-2022 | 203 /BSSD | 15/06/2021 | 15/07/2021 | SACHIN KUMAR SARKAR | 4.96 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Muchipara under Rasa Mouza (J.L. No.107) under Khoyrasole Block within the command area of RASA Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.24) | AE |  | ORD/000021/2021-2022 | 201 /BSSD | 15/06/2021 | 15/07/2021 | ASIT GHOSH | 4.95 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kayastaparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 22) | AE | JE1 | ORD/000006/2021-2022 | 199/BSSD | 15/06/2021 | 15/07/2021 | B.M.SARKAR | 4.95 | 4.91 | 99.15 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Bauriparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 21) | AE | JE1 | ORD/000007/2021-2022 | 198/BSSD | 15/06/2021 | 15/07/2021 | DIPAK SARKAR | 4.85 | 4.7 | 96.95 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Muchiparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte.(Sl. No. - 24)) | AE | JE1 | ORD/000009/2021-2022 | 201/BSSD | 15/06/2021 | 15/07/2021 | ASIT GHOSH | 4.95 | 4.95 | 100 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Dompara & Coloney under Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 28) | AE | JE1 | ORD/000010/2021-2022 | 203/BSSD | 15/06/2021 | 15/07/2021 | SACHIN KUMAR SARKAR | 4.96 | 4.96 | 100 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Keotparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 23) | AE | JE1 | ORD/000008/2021-2022 | 200/BSSD | 15/06/2021 | 15/07/2021 | BHABATARAN SADHU | 4.98 | 4.96 | 99.44 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Chasapara under RASA Mouza (J.L. No.107) under Khoyrasole Block within the command area of RASA Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.26) | AE | JE1 | ORD/000022/2021-2022 | 202/BSSD | 15/06/2021 | 15/07/2021 | ARKA JYOTI GHOSH | 4.79 | 0 | 0 | 100
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Jamrand Chasapara under Jamrand Mouza (JL No. - 136) under Khoyrasole Block, within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 31) | AE | JE2 | ORD/000011/2021-2022 | 206 /BSSD | 15/06/2021 | 15/07/2021 | SUMEN CHOWDHURY | 4.97 | 0 | 0 | 100
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Acharjyapara under Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte.(Sl. No. - 25) | AE | JE1 | ORD/000013/2021-2022 | 212/BSSD | 15/06/2021 | 15/07/2021 | GOUTAM MONDAL | 4.95 | 4.94 | 99.78 | 0
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block | SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasa in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.(Sl. No.9) | AE | JE1 | ORD/000410/2022-2023 | 2587/BHM | 22/11/2022 | 21/01/2023 | HIRANMAY GHOSH | 58.98 | 0 | 0 | 49
Total | [13 empty] | 156.98 | 29.42 | 18.74