## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum | SM/08171 | Retrofitting | Additional Supply of UPVC Pipe & strainer 200 mm dia for Sinking of 09 Nos 200mm dia. X 30 mtr deep River bed Tube Well including trial bore for Puranagram Piped Water Supply Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000666/2021-2022 | 118/RSD | 11/03/2022 | 10/04/2022 | RUBAL CONSTRACTION | 1.48 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum | SM/08171 | Retrofitting | Balance Work for Construction of High Lift Pump House Construction of Ramp,PCC Apporch Road at CWR site for Puranagram Piped Water Supply Scheme under Rampurhat Sub-Division withen Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000533/2021-2022 | 19/RSD | 04/01/2022 | 03/02/2022 | GOLAM RASUL | 3.88 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum | SM/08171 | Retrofitting | Construction of Boundary Wall at Puranagram Piped Water Supply Scheme under under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000637/2020-2021 | 1636/BHM | 15/12/2020 | 13/02/2021 | GOLAM RASUL | 4.27 | 0 | 0 | 35
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum | SM/08171 | Retrofitting | Construction of Boundary Wall at Puranagram CWR Site for Puranagram Piped Water Supply Scheme under Md. Bazar block under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000625/2020-2021 | 20/RSD | 11/01/2021 | 12/03/2021 | GOLAM RASUL | 4.05 | 0 | 0 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum | SM/08171 | Retrofitting | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Puratangram Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿(Sl. No.14) | AE | JE3 | ORD/000659/2020-2021 | 134/BHM | 25/01/2021 | 26/03/2021 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 82.45 | 82.11 | 99.59 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum | SM/08171 | Retrofitting | Connection between New Tubewells to existing CWR and Laying of Rising Main from Highlift Pumphouse to OHR with DI K9 under Puranagram Piped Water Supply Scheme under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. | AE | JE3 | ORD/000519/2021-2022 | 13/RSD | 04/01/2022 | 03/02/2022 | RUBAL CONSTRACTION | 4.52 | 0 | 0 | 100
Total | [13 empty] | 100.65 | 82.11 | 81.57